## Applicant
APPLICATION FORM
|  | Voda pre klímu - environmentálne technológie o.z. | [7 empty] | Version 2
| Project Application version |  |  | 2 |  |  |  |  | Call code | ACC04
1. Summary
1.1 Project Title
Save wetland together
1.2 Programme Title
| ACC |  | Climate Change Mitigation and Adaptation
1.3 Programme Outcome
| ACC_OTC2 |  | Enhanced ability of targeted ecosystems to adapt to climate change
1.4 Programme Output
Restoration of degraded wetland ecosystems
1.5 Location of Project implementation and Applicant’s registered address
|  | Self-governing region, in which most of the activities will be implemented (select) |  |  | Banskobystrický
|  | District (select) |  |  | Žiar nad Hronom
|  | Another district (select if relevant) |  |  | Banská Štiavnica
Another district (select if relevant)
Another district (select if relevant)
|  | Applicants' registered address - self-governing region (select) |  |  | Trnavský
|  | District (select) |  |  | Senica
2. Applicant
2.1 Name and contact details
| 2.1.1 Full legal name: |  | Voda pre klímu - environmentálne technológie o.z.
y
| 2.1.2 Sector |  |  |  |  | Not-for-profit Sector
| 2.1.3 Legal form of the organisation |  |  |  |  | Civic association (o.z.)
2.1.4 Other legal form of the organisation - specify
| 2.1.5 Legal form under the Donors' classification |  |  |  |  | Non-Governmental organisation (NGO)
| 2.1.6 Organisation identification number (IČO) | [6 empty] | 42157986
2.1.7 Registered address:
|  | Street: | Kalinčiakova
Descriptive and orientation number:
|  |  | 298 | 10
|  | Postal code: | 90501
|  | Town/City: | Senica
|  | Internet address: | https://vodapreklimu.sk
2.1.8 Contact person
|  |  | Title | Name |  |  | Surname
|  | Name: | Mr | Ivan |  |  | Matušek
|  | Job position: | Statutory - Chairman of the organization
|  | Email: | ivanmatusek30@gmail.com
|  |  | Prefix |  | Number
|  | Phone: | +421
|  | Mobile Phone: | +421 | 917325597
2.1.9 Contact address of the organisation if different from the registered address
|  | Organisation: | Voda pre klímu - environmentálne technológie o.z.
|  | Street: | Oravné
Descriptive and orientation number:
|  |  | 6078 | 8
|  | Postal code: | 91701
|  | Town/City: | Trnava
2.2 Description of the Applicant
2.3 How you learned about the availability of the Grant
|  | (select) | minzp.sk/eea / minzp.sk/en/eeagrants/eea-norway-grants/
3. Project
3.1. Project summary
3.2. Project activities
Title of Activity 1
Wetland revitalization
Relates to output
Restoration of degraded wetland ecosystems
Description of Activity 1
Title of Activity 2
Net monitoring
Relates to output
Restoration of degraded wetland ecosystems
Description of Activity 2
Title of Activity 3
Awareness raising campaign
Relates to output
Restoration of degraded wetland ecosystems
Description of Activity 3
Title of Activity 4
Publicity and Communication
Relates to output
Restoration of degraded wetland ecosystems
Description of Activity 4
Title of Activity 5
Relates to output
Restoration of degraded wetland ecosystems
Description of Activity 5
Title of Activity 6
Relates to output
Restoration of degraded wetland ecosystems
Description of Activity 6
Title of Activity 7
Relates to output
Restoration of degraded wetland ecosystems
Description of Activity 7
Title of Activity 8
Relates to output
Restoration of degraded wetland ecosystems
Description of Activity 8
3.3. Project Indicators
3.3.1 Standard indicators
|  | Indicator - title |  | Type | Level | Baseline | Target | Describe how the indicator is measured |  |  | Code
|  | Estimated number of people benefiting from ecosystems improvement measures |  | Reported | Outcome | 0 | 63613 | The data is related to the number of inhabitants of the district of Banská Štiavnica and Žiar nad Hronom according to the Statistical Office of the Slovak Republic. Involvement of the general public, school students, professional public during the visit to the individual project locations in filling in the questionnaire with relevant questions concerning the positive impact of the project. |  |  | ACC_OTC2_IND1
|  | Improved environmental status of supported ecosystems |  | Reported | Outcome | No | Yes | 4 localities will be revitalized with 4 wetlands and peatlands. The effects of implemented measures will be monitored through a monitoring net. A final report will be prepared for each site. Photodocumentation, video from sites. |  |  | ACC_OTC2_IND2
|  | Estimated area of wetland ecosystems restored (in m2) |  | Binding | Output | 0 | 196668.2 | 4 localities will be revitalized with 4 wetlands and peatlands. The effects of implemented measures will be monitored through a monitoring net. A final report will be prepared for each site. Photodocumentation, video from sites. |  |  | ACC_OTC2_OTP1_IND1
|  | Number of awareness campaigns carried out |  | Binding | Output | 0 | 1 | Photo documentation and attendance lists of participants will be prepared from each information campaign. |  |  | ACC_OTC2_OTP1_IND2
|  | Number of wetland ecosystems supported |  | Binding | Output | 0 | 4 | 4 localities will be revitalized with 4 wetlands and peatlands. The effects of implemented measures will be monitored through a monitoring net. A final report will be prepared for each site. Photodocumentation, video from sites. |  |  | ACC_OTC2_OTP1_IND3
3.3.2 Bilateral indicators (only relevant if a Donor Project Partner is involved in the Project)
|  | Indicator - title |  | Type | Level | Baseline | Target | Describe how the indicator is measured |  |  | Code
|  | Number of Projects involving cooperation with a Donor Project Partner (disaggregated by Donor State) |  | Binding | Output | 0 | 1 | Copies of contracts, partnersheep agreements |  |  | ACC_OTCB_OTP1_IND1
|  | Number of training courses co-organised by donor state and beneficiary state entities |  | Binding | Output | 0 | 4 | Opening session, closure session, presentation on Appied Natural Sciences conference, workshop in Norway. Photo documentation and attendance lists of participants will be prepared from each information campaign? Time sheet. |  |  | ACC_OTCB_OTP1_IND2
3.3.3 Publicity indicators
|  | Indicator - title |  |  |  | Baseline | Target | Describe how the indicator is measured |  |  | Code
|  | Number of information events |  |  |  | 0 | 8 | Photo documentation and attendance lists of participants will be prepared from each information campaign. In the case of press releases, a scan of the tall message will be performed. |  |  | PBL_IND1
|  | Number of participants at information events |  |  |  | 0 | 200 | Photo documentation and attendance lists of participants will be prepared from each information campaign. |  |  | PBL_IND2
|  | Number of website visits |  |  |  | 0 | 3000 | The applicant will create and regularly update a website on the existing website of the organization www.vodapreklimu.sk . information about the project published on this website will be published in Slovak and English. Counting traffic to the recipient's website will be done through google analytics. In addition to the described mandatory indicator, links to project information from the applicant's website will be placed on all partners' websites. |  |  | PBL_IND3
|  | Number of presentations of the project on other events, publications about the Project |  |  |  | 0 | 5 | Photo documentation and attendance lists of participants will be prepared from each information campaign. In the case of press releases, a scan of the tall message will be performed. |  |  | PBL_IND4
|  | Number of promotional material produced within Project |  |  |  | 0 | 500 | Printed publication on reconstructed wetlands. | publicity_indicator_measurement5 |  | PBL_IND5
|  | Number of media outputs |  |  |  | 0 | 2 | During the project will be created 2 video documents of the reconstracted wetlands and they will be promoted on regional TV and Youtube. | publicity_indicator_measurement6 |  | PBL_IND6
3.3.4 Project specific indicators (not relevant for the Call ACC04)
|  | Indicator - title |  | Type | Level | Baseline | Target | Describe how the indicator is measured |  |  | Code
3.4 Basic statistical data on the Project
3.4.1 Sector code according to the OECD classification (choose the main sector the Project is aimed at):
|  | Main sector | Specification | [5 empty] | Sector code
|  | Environment and Climate Change | Climate change mitigation | [5 empty] | 4101004
3.4.2 Main measures of the Project (select at least one and assign its importance)
|  |  | Information and awareness raising |  |  |  |  | main measure
Advocacy
|  |  | Research |  |  |  |  | secondary measure
|  |  | Infrastructure development and provision of equipment |  |  |  |  | secondary measure
Capacity-building
|  |  | Education and training |  |  |  |  | secondary measure
Provision of services
3.4.3 If the Project is a research one, fill in the following fields: (not relevant for the Call ACC04)
Research type:
Academic field:
Discipline:
3.5 Project target groups
Select the three most important Project target groups, i.e. the groups the Project is aimed at.
|  | Category |  | Specification |  |  | Intermediary | Beneficiary
| 1 | Education/ research-related |  | Students (any age) |  |  |  | x
| 2 | Education/ research-related |  | NEETs (not in education, employment or training) |  |  |  | x
| 3 | Work-related |  | Unemployed |  |  |  | x
4 Project management
4.1 Structure of Project management including financial management
4.2 Partnership
| Partners Basic Data |  | Partner1 |  | Partner2 |  | Partner3 |  | Partner4
| Full Legal Name of the Partner: |  | Štátna ochrana prírody Slovenskej republiky |  | Základná škola s materskou školou Maximiliána Hella |  | Univerzita sv. Cyrila a Metoda v Trnave |  | Norges miljø- og biovitenskapelige universitet
| Name of the Partner (in English): |  | State Nature Conservancy of the Slovak Republic |  | The Primary & Secondary School of Maximilian Hell |  | University of Ss. Cyril and Methodius in Trnava |  | Norwegian University of Life Science
| Organisation ID (IČO) or equivalent |  | 17058520 |  | 37831127 |  | 36078913 |  | 969159570
|  | Sector: | Public Sector |  | Public Sector |  | Public Sector |  | Public Sector
|  | Partner's legal form: | State budgetary or allowance organisation |  | Budgetary or allowance organisation of municipality |  | State budgetary or allowance organisation |  | State budgetary or allowance organisation
Specify the legal form, if other:
| Legal form - Donors classification |  | Government |  | Regional authority |  | Government |  | Government
| Registered address |  | Partner1 |  | Partner2 |  | Partner3 |  | Partner4
| Street: |  | Tajovského |  | Štiavnické Bane |  | Námestie Jozefa Herdu |  | Universitetstunet
| Descriptive/orientation number: |  | 14440/288 |  | 128 |  | 577/2 |  | 3
| Postal Code: |  | 97401 |  | 96981 |  | 91701 |  | 1433
| Town/City: |  | Banská Bystrica |  | Štiavnické Bane |  | Trnava |  | Ås
| Country: |  | Slovakia |  | Slovakia |  | Slovakia |  | Norway
| Internet address: |  | http://www.sopsr.sk |  | https://www.zakladnaskola.com/ |  | https://www.ucm.sk |  | www.nmbu.no
| Contact persons |  | Partner1 |  | Partner2 |  | Partner3 |  | Partner4
| Name: |  | Ing. Peter Farbiak |  | Mgr. Pavol Michal |  | doc. RNDr. Miroslav Horník, PhD. |  | Elisabeth Iversen
| Job position: |  | director |  | director |  | head of department |  | Elisabeth Iversen
| Email: |  | peter.farbiak@sopsr.sk |  | pavel.michal@hotmail.com |  | miroslav.hornik@ucm.sk |  | elisabeth.iversen@nmbu.no
| Phone: |  | +421 45 691 1931 |  | N/A |  | N/A |  | +47 67 23 00 00
| Mobile phone: |  | +421 903 298 326 |  | +421 905 258 847 |  | +421907723787 |  | N/A
| Financing and status |  | Partner1 |  | Partner2 |  | Partner3 |  | Partner4
| Does the Partner spend the Project Grant? |  | Yes |  | Yes |  | Yes |  | Yes
| Does the Partner co-finance the Project? |  | Yes |  | No |  | No |  | No
| Project Grant shall be paid to Partner as: |  | Advance payments |  | Advance payments |  | Advance payments |  | Advance payments
| Actual status of partnership: |  | Partnership Statement signed |  | Partnership Statement signed |  | Partnership Statement signed |  | Partnership Statement signed
4.3 Roles of Partners
Role of Partner 1 in the Project
Role of Partner 2 in the Project
Role of Partner 3 in the Project
Role of Partner 4 in the Project
4.4 Bilateral partnership
(fill in this part only if there is at least one Donor Project Partner involved in the Project)
4.4.1 What level of involvement do you foresee for your Donor Project Partner(s)?
[Multiple choice list – if multiple Donor Project Partners provide the overall perspective]
|  |  | Attend events in our Project |  |  |  |  | Yes
|  |  | Contribute with presentations and/or input to events |  |  |  |  | Yes
Provide capacity building in our Project (in the form of training, etc.)
|  |  | Work with us to find common solutions to shared challenges in the Project |  |  |  |  | Yes
Other - specify
4.4.2 How was the cooperation established?
[Multiple choice list – if multiple Donor Project Partners provide the overall perspective]
|  |  | Previous cooperation |  |  |  |  | Yes
Match making event under the Programme
Programme operator/ Fund operator
Direct assistance by Donor Programme Partner or Donor Contact Point
Search in the partnership database (Innovation Norway database, Norwegian Helsinki Committee, others)
Embassy assistance
Independent search for Partner
Other - specify
5. Project plan
5.1 Financing
|  | Category/Entity |  |  | Applicant | Partner1 | Partner2 | Partner3 | Partner4 | TOTAL
| 5.1.1. | Direct expenditure (EUR) |  |  | 234856 | 377432 | 74500 | 53500 | 30845 | 771133
| 5.1.2. | Indirect costs (EUR) |  |  | 19569 | 9888 | 1575 | 2000 | 5975 | 39007
|  | Indirect costs calculation method |  |  | Article 8.5.1c) | Article 8.5.1c) | Article 8.5.1c) | Article 8.5.1c) | Article 8.5.1b)
| 5.1.3. | Reserve (EUR) |  |  | 10000 | 18000 | 3000 | 500 | 1500 | 33000
| 5.1.4. | In-kind contributions (EUR) |  |  | 44000 |  |  |  |  | 44000
| 5.1.5. | Cash Co-financing (EUR) |  |  | 41000 | 4000 | 0 | 0 | 0 | 45000
| 5.1.6. | First advance requested (EUR) |  |  | 44685 | 80264 | 15815 | 11200 | 7664 | 159628
| 5.1.7. | Project Grant requested (EUR) |  |  | 223425 | 401320 | 79075 | 56000 | 38320 | 798140
| 5.1.8. | Total Eligible Cash Expenditure (EUR) |  |  | 264425 | 405320 | 79075 | 56000 | 38320 | 843140
| 5.1.9. | Total Eligible Expenditure (EUR) |  |  | 308425 | 405320 | 79075 | 56000 | 38320 | 887140
| 5.1.10. | [7 empty] | Indirect costs (% on staff costs) | 12.25%
| 5.1.11. | [7 empty] | Project Grant Rate (%) | 89.97%
| 5.1.12. | [7 empty] | Maximum Grant Rate (%) | 90%
| 5.1.13. | [7 empty] | Minimum Project Grant Requested (EUR) | 200000
| 5.1.14. | [7 empty] | Maximum Project Grant Requested (EUR) | 1000000
| 5.1.15. | [7 empty] | Maximum Reserve (EUR) | 44357
| 5.1.16. | [7 empty] | Maximum in-kind (% on co-financing) | 50%
| 5.1.17. | [7 empty] | Maximum in kind (EUR) | 44376
| 5.1.18. | [7 empty] | Actual in-kind (% on co-financing) | 49.44%
| 5.1.19. | [7 empty] | Contribution from the EEA/Norway Grants | 678419
| 5.1.20. | [7 empty] | Contribution from the Slovak State Budget | 119721
5.2 Milestones
| 5.2.1. | Expected Project implementation duration (in months following the signature of the Project Contract) | [6 empty] | within 36 months
| 5.2.2. | List of Milestones |  |  |  | Relates to activity | General classification | Importance | Milestone implementation started/completed (following the signature of the Project Contract)
[9 empty] | Started | Completed | Duration (months)
| 1 | Opening meeting |  |  |  | Activity4 | Publicity-related | Fundamental | within 1 months | within 3 months | 2
| 2 | Project detailed design of net monitoring |  |  |  | Activity2 | Permits-related | Essential | within 1 months | within 3 months | 2
| 3 | Preparation of 3D model |  |  |  | Activity3 | Publicity-related | Essential | within 1 months | within 6 months | 5
| 4 | Web sites promotion of the project |  |  |  | Activity4 | Publicity-related | Fundamental | within 1 months | within 6 months | 5
| 5 | Detail design documentation of Information point Trnava |  |  |  | Activity3 | Permits-related | Essential | within 1 months | within 6 months | 5
| 6 | Project detail design documentation of wetlands measures |  |  |  | Activity1 | Permits-related | Essential | within 1 months | within 6 months | 5
| 7 | Finish of procurement |  |  |  | Project Management | Procurement-related | Essential | within 1 months | within 6 months | 5
| 8 | Popular publication of wetland general |  |  |  | Activity3 | Procurement-related | Relevant | within 1 months | within 12 months | 11
| 9 | Opening of Information point Stiavnicke bane |  |  |  | Activity3 | Publicity-related | Fundamental | within 1 months | within 12 months | 11
| 10 | Installation and start of operation of monitoring net |  |  |  | Activity2 | Others | Relevant | within 1 months | within 12 months | 11
| 11 | Opening of Information point Trnava |  |  |  | Activity3 | Publicity-related | Essential | within 1 months | within 12 months | 11
| 12 | Initial treatment of wetland Gajdosovo finished |  |  |  | Activity1 | Others | Relevant | within 1 months | within 18 months | 17
| 13 | Educational trail wetland Gajdosovo |  |  |  | Activity3 | Publicity-related | Essential | within 6 months | within 18 months | 12
| 14 | Publication Wetlands for children |  |  |  | Activity3 | Publicity-related | Essential | within 1 months | within 18 months | 17
| 15 | Preparation and installation of information boards |  |  |  | Activity3 | Publicity-related | Fundamental | within 6 months | within 18 months | 12
| 16 | Hydrologic studies finished |  |  |  | Activity3 | Publicity-related | Essential | within 1 months | within 18 months | 17
| 17 | Water retention measures finished |  |  |  | Activity1 | Others | Essential | within 6 months | within 24 months | 18
| 18 | Report of research on behavioral and student behavioral change |  |  |  | Activity3 | Publicity-related | Essential | within 6 months | within 24 months | 18
| 19 | Presentation of the project on on Applied Natural Sciences conference |  |  |  | Activity4 | Publicity-related | Fundamental | within 24 months | within 36 months | 12
| 20 | Report interpretation of results of research |  |  |  | Activity1 | Publicity-related | Essential | within 6 months | within 36 months | 30
| 21 | Final web sites promotion |  |  |  | Activity4 | Publicity-related | Fundamental | within 12 months | within 36 months | 24
| 22 | Closure meeting |  |  |  | Activity4 | Publicity-related | Fundamental | within 24 months | within 36 months | 12
| 23 | Project final report |  |  |  | Project Management | Publicity-related | Essential | within 24 months | within 36 months | 12
| 24 | Project final financial report |  |  |  | Project Management | Publicity-related | Essential | within 24 months | within 36 months | 12
| 25 | Project final publicity report |  |  |  | Project Management | Publicity-related | Essential | within 24 months | within 36 months | 12
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
6. Legal issues
6.1 Project compliance with the relevant legislation and strategic documents
6.2 Proprietary relations to real estate and property that is the object of the Project
6.3 Permits necessary for Project implementation
7. Communication plan
8. Risks and risks management
| Risk description |  |  | Type | Likelihood | Consequence | Risk score | Response to risk | Description of response
| Exceeding the planned time or project budget. |  |  | Programmatic | Unlikely | Moderate | 2 | Avoid / terminate | The development of the project will be monitored on monthly bases by project manager and in the cases of indicators will be prepared measures.
| Obstacles due to force majeure, e.g. the epidemiological situation and their impact on information and publication activities |  |  | Programmatic | Likely | Minimal | 1.73 | Transfer / share | All the activities concerned will be carried out in a distance form using internet tools.
| Delays in legislative permits related to project implementation |  |  | Programmatic | Very unlikely | Minimal | 1 | Avoid / terminate | The related permits will be processed in advance before the start of the project.
| Problems with the implementation of public procurement. Non transparent procurement. |  |  | Operational | Very unlikely | Minimal | 1 | Avoid / terminate | Public procurement will be managed by a public procurement specialist.
| Adverse weather conditions for field work. |  |  | Operational | Very unlikely | Minimal | 1 | Avoid / terminate | The work will be operationally rescheduled without impact on the project schedule and budget.
| Failure of network monitoring devices or other technology. For example, office. |  |  | Operational | Unlikely | Minimal | 1.41 | Mitigate | Contractual service of devices and equipment will be provided.
| Failure of a project team member. |  |  | Operational | Very unlikely | Minimal | 1 | Transfer / share | After discussion and approval by the program governing body, he will be replaced by another member of the team.
9. Cross-cutting issues
Policy markers (see guidance in the Results Reporting Guide)
| Gender equality | [8 empty] | Relevant
| Roma inclusion and empowerment | b. Roma inclusion and empowerment | b. Roma inclusion and empowerment | b. Roma inclusion and empowerment | b. Roma inclusion and empowerment | b. Roma inclusion and empowerment | b. Roma inclusion and empowerment | b. Roma inclusion and empowerment | b. Roma inclusion and empowerment | Relevant
| Social inclusion of vulnerable groups other than Roma | c. Social inclusion of vulnerable groups other than Roma | c. Social inclusion of vulnerable groups other than Roma | c. Social inclusion of vulnerable groups other than Roma | c. Social inclusion of vulnerable groups other than Roma | c. Social inclusion of vulnerable groups other than Roma | c. Social inclusion of vulnerable groups other than Roma | c. Social inclusion of vulnerable groups other than Roma | c. Social inclusion of vulnerable groups other than Roma | Relevant
| Anti-discrimination | d. Anti-discrimination | d. Anti-discrimination | d. Anti-discrimination | d. Anti-discrimination | d. Anti-discrimination | d. Anti-discrimination | d. Anti-discrimination | d. Anti-discrimination | Relevant
| Transparency and anti-corruption | [8 empty] | Relevant
10. Project Revenues and Sustainability
10.1 Costs and Revenues
[8 empty] | Are real estate investments included in the Project eligible costs (purchase, reconstruction)? | Yes
[8 empty] | Minimum Project sustainability period following the Final Project Report approval | 5 years
Fill in the table and identify the estimated Project costs and revenues during the entire period of the Project sustainability
| COSTS |  |  |  | YEAR |  |  |  |  | TOTAL
[5 empty] | N | N+1 | N+2 | N+3 | N+4
| Labour Costs |  |  |  | 7800 | 7800 | 7800 | 7800 | 7800 | 39000
| Running Costs |  |  |  | 8000 | 8000 | 8000 | 8000 | 8000 | 40000
| Investment Costs |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Other - specify | [8 empty] | 0
| Other - specify | [8 empty] | 0
| Other - specify | [8 empty] | 0
| Other - specify | [8 empty] | 0
| Other - specify | [8 empty] | 0
| TOTAL |  |  |  | 15800 | 15800 | 15800 | 15800 | 15800 | 79000
| REVENUES |  |  |  | YEAR |  |  |  |  | TOTAL
[5 empty] | N | N+1 | N+2 | N+3 | N+4
| Revenues from selling goods and services |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Property revenues |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Rental revenues |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Grants and donations received |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Other - specify | [8 empty] | 0
| Other - specify | [8 empty] | 0
| Other - specify | [8 empty] | 0
| Other - specify | [8 empty] | 0
| TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
10.2 Sources of financing the sustainability of Project Outputs
11. Application annexes
11.1. Compulsory annexes to be submitted along with the Project Application
| # | Title | [7 empty] | Prescribed Form | Document submitted
| 1 | Project Budget as templated in the Project Application Form | [7 empty] | Yes | Yes
| 2 | Plan for restoration of degraded wetland ecosystem | [7 empty] | Yes | Yes
| 3 | Partnership statement, Letter of intent or similar document (if Project is realized in partnership) | [7 empty] | No | Yes
| 4 | Declaration stating that the activities carried out within the Project will be used only for non-economic purposes | [7 empty] | Yes | Yes
| 5 | Cadastral map with delineated target area and the location of all technical measures planned within the Project | [7 empty] | No | Yes
| 6 | Agreement of owner or operator/tenant of all lands concerned, where technical measures are planned, with Project realization | [7 empty] | No | Yes
| 7 | Agreement of operator or tenant/borrower of watercourse, or its integral tract, with Project realization (if relevant). | [7 empty] | No | Yes
| 8 | Consent/Supporting opinion of the Department of Protection of Nature, Biodiversity and Landscape of Ministry of Environment of the Slovak Republic to the Project plan | [7 empty] | No | Yes
11.2. List of optional annexes
| 1 | Znalecký posudok pre cenu pozemku Gajdošovo - Expert opinion for the price of land Gajdošovo
| 2 | Detailný harmonogram projektu - Detailed project schedule
| 3 | Zmluva o budúcej zmluve - Contract for a future contract
4
Notes
12. List of consultants
The following persons have been involved in the preparation of this Project Application:
|  | # | Name |  | Position |  |  | Organisation
|  | 1 | Ivan Matušek |  | project manager |  |  | Applicant / Water for Climate - environmental technologies
|  | 2 | Natália Cziroková |  | asistant of project manager |  |  | Applicant / Water for Climate - environmental technologies
|  | 3 | Elisabeth Iversen |  | University represetative |  |  | Partner 4 / Norges miljø- og biovitenskapelige universitet
|  | 4 | Miroslav Horník |  | Head of university department |  |  | Partner 3 / University of Ss. Cyril and Methodius in Trnava
|  | 5 | Slavomír Buci |  | research worker |  |  | Partner 1 / State Nature Conservancy
|  | 6 | Monika Farbiakova |  | research worker |  |  | Partner 1 / State Nature Conservancy
|  | 7 | Lucia Mišíková |  | teacher |  |  | Partner 2 / The primary and Secondary School of Maximilian Hell
|  | 8 | Pavol Michal |  | director |  |  | Partner 2 / The primary and Secondary School of Maximilian Hell
13. Statutory declaration
I hereby declare that I am duly authorized to submit this Project Application (hereinafter referred to as “Application”) in the name of my organization and that I had thoroughly reviewed all statements and information provided herein and that they are true, correct and accurate. I confirm that this Project will be carried out as described in this Application and that the Grant requested reflects correctly what is reasonably needed as a minimum for the Project to proceed and to be completed. I hereby declare that if the Project is supported, the Ministry of Environment of the Slovak Republic (Programme Operator), Ministry of Investments, Regional Development and Informatization of the Slovak Republic (National Focal Point) and the Financial Mechanism office (FMO) may publish the summary of the Project and/any information contained in this Application that they deem necessary under their sole discretion on their web sites. By signing the Application, I request granting the first advance payment in accordance with the terms of the Call.
I hereby declare that any documents required to be submitted before the conclusion of the Project Contract shall be submitted a and will be submitted accurately, correctly and without changing any of the data.
I hereby declare that all the results of the Project shall be available to the public during the in-force period of the Project Contract and under the terms specified in the Project Contract. In this regard, I hereby declare that I accept full responsibility for the settlement of all claims related to but not limited to the publication of these results and/ or this Application, so their disclosure cannot be considered as a breach of the relevant legislation, for example the Copyright Act, Commercial Code and the Law on Personal Data Protection. To this end, by submitting this Application I also consent to the Privacy Statement listed in Annex 1 to the Guideline for Applicant. My organization shall defend the Ministry of Environment of the Slovak Republic and hold harmless against any third party claims that relating to but not limited to the publication of the above mentioned.
I hereby declare that the Applicant and the Partners:
- have settled financial relations with the state budget;
- do not have tax liabilities;
- do not have health insurance, social insurance and retirement savings liabilities;
- did not violate the prohibition of illegal work and illegal employment under special legislation for the period of its effectiveness (1 April 2005) and in case of illegal employment of foreigner under § 2. 2 point. c) of Act. 82/2005 Coll. on illegal work and illegal employment and amending certain acts for a period of five years from the violation of this prohibition
I hereby declare that no significant change shall occur in the period from the submission of the Application until the conclusion of the Project Contract, which:
a) affects the nature of the Project or its implementation, or which provides an unfair advantage to any entity
b) relates to the change in the ownership of an infrastructural item or a part of it, or the abortion of production activities.
I am aware that in case of violation of this declaration or these declarations, the Grant may not be granted and thus the Ministry of Environment of the Slovak Republic is entitled to request the entire amount of the Grant provided. By submitting this Application I consent to this Declaration and to all of the above mentioned (even, if the Application is not signed).
|  |  | Statutory |  |  |  | Second statutory, if needed
|  | Name | Ivan Matušek
Signature (and stamp), if relevant
|  | Job Position | Chairman of the Applicant organisation
|  |  | Day | Month | Year |  | Day | Month | Year
|  | Date | 18 | 10 | 2021
Note on C656: Read the Applicants Guide for detailed information. The method according to Article 8.5.1.c) is highly recommended
Detail description of Project location:
The project is focused on 4 localities with corrupt wetland ecosystems: 1. Kremnica - Bartošova Lehôtka, 2. Kremnica - Kopernica, 3. Banská Štiavnica - CHA Michalštôlnianske rašelinisko, 4. Banská Štiavnica - PR Gajdošovo. All sites are located in the Banská Bystrica region in two districts: Banská Štiavnica and Žiar nad Hronom. In this area, all field work, installation of the monitoring system and also part of information and educational activities that are associated with staying in the field directly in the wetland will be carried out. A large part of information and educational activities will be implemented in cooperation with the partner of the elementary school Štiavnické Bane, also in the district of Banská Štiavnica and a certain part of educational and information activities will be implemented in the Trnava self-governing region, Trnava District in cooperation with partner UCM Trnava and Voda pre klímu.
a) Project relevance (including synergy with other Projects contributing to climate change adaptation and mitigation in target area, if relevant):
There are 66 habitat types of European importance in Slovakia, of which 24 are classified as aquatic, river wetlands, or dependent on the aquatic environment. These habitats have high natural and ecosozological value. They allow the existence of the number of native species of plants and animals, many of which are rare and protected.
Wetland habitats, which represent the most valuable parts of nature, are directly dependent on the aquatic environment. Their local occurrence, threat, sensitivity and specific character make them among the rarest elements of our nature. In the past, the most sites of this habitat have been derived, converted into fields, pastures or built up. At present, it is ​​less than 0.5% of the area of ​​Slovakia. Their conservation and restoration not only increases natural values, but also contributes to capturing floodwaters, improving water quality, replenishing groundwater supplies, and balancing friends in streams.
b) Project objective:
The aim of the project is restoration of 4 sites with degraded wetlands: Kremnica - Bartošova Lehôtka Lower peat bog and Upper peat bog ecosystem sum area: 2 114 m2, Kremnica – Kopernica peat bog ecosystem area 10 890 m2, Štiavnica – Michalka peat bog ecosystem area 846 m2, Štiavnica – Gajdošovo peat bog ecosystem area 182 820 m2. In addition, the wetland on the school premises in Štiavnické Bane will be reconstructed as 5th sites of the project.
c) Expected Project results/outputs:
The primary purpose of revitalization measures is the restoration of processes indicating the natural development of the wetland system in the micro-basin and its inherent functions such as: free movement of water, accumulation and retention of water in forest ecosystems around peatlands, communication with groundwater , balancing of runoff conditions by infiltration and refilling of water in dry periods, water retention in the country to restore the small water cycle, slowing down of flows during torrential rains using accumulation in sedimentation polders and seepage pits, creation of refugees and breeding sites for amphibians and reptiles, supporting diversity and ecological stability in the territory, microclimate regulation, the ability of ecosystems to adapt to climate change and to mitigate adverse impacts, landscaping, aesthetic and recreational function, prevent the inflow of polluted water into natural ecosystems from existing export routes created in connection with mining activities, eliminate the negative impact of mining activities on the natural ecosystems in the area of interest, to achieve a favorable status of wetland habitats and species according to the publication: Favorable status of habitats and species (ŠOP SR, 2005).
d) Main activities including mandatory activities defined in the Call text (Chapter 4):
Activity 1 Restoration of degraded wetland ecosystems :
Kremnica - Bartošova Lehôtka Implementation: for lower peat bog: to determine exactly the inflow and outflow conditions of water in the peat bog, subsidize the peatland with water throughout the growing season, retaining a sufficient amount of water above the peat bog and ensuring its continuous distribution to the peat bog even during dry periods, change or retreat to achieve the disappearance or complete extinction of the expanding species Molinia caerulae, maintain a high abundance of Drosera rotundifolia. Upper peat bog, to determine exactly the inflow and outflow conditions of water in the peat bog, ensure that the wetland is subsidized by sufficient unpolluted water throughout the growing season, extend the area of ​​the peat bog to the original area, maintain a high abundance of Drosera rotundifolia
Kremnica – Kopernica Implementation: to determine exactly the inflow and outflow conditions of water in the peat bog, during the project, expand the area of ​​the peat bog to the original area at the expense of the floodplain forest, suitably direct the inflow of water into individual parts of the wetland, divert the flow of bentonite-contaminated flushing water from roads outside the wetland, to improve the state of the floodplain forest habitat in the lower part of the wetland, restitute species Drosera rotundifolia
Štiavnica – Michalka Implementation: to determine exactly the inflow and outflow conditions of water in the peat bog, subsidize the peatland with water throughout the growing season, retention of a sufficient amount of water above the peat bog as well as in the peat bog and ensure its continuous distribution even during dry periods and slowing down the outflow of water from the peat bog, change or retreat to achieve the disappearance or complete extinction of the expanding species Molinia caerulae, increase the abundance of Drosera rotundifolia, extend the area of ​​the peat bog to the original area
Štiavnica – Gajdošovo Implementation: accurately determine the inflow and outflow conditions of water in the wetland, ensure that the wetland is subsidized by sufficient unpolluted water throughout the growing season, retaining a sufficient amount of water above the wetland as well as in the wetland and ensuring its continuous distribution even during dry periods and slowing down the outflow of water from the wetland, suitably direct the inflow of water into individual parts of the wetland, during the project, expand the wetland area to the original area at the expense of tree vegetation, temporarily completely exclude cattle grazing in the vicinity and in the Gajdošovo Nature Reserve.
School wetland - The revitalization of the wetland will consist of the exchange of soil, the planting of suitable wetland plants and the extension of water retention measures. Part of the revitalization of the wetland at the Primary and Secondary school of Maximilian Hell will also include the installation of information boards showing the implementation of works in natural localities will be covered by the partner 1, the revitalization of the wetland in the school area will be covered by the partner 2. The project applicant together with the partner 3 and the Norwegian partner 4 will provide technical support..
Activity 2 Net monitoring
As part of this activity, a permanent monitoring network will be installed at 4 sites of natural wetlands, which will collect data on local meteorological conditions. The implementation of the monitoring network will be covered by the partner 1. The project applicant together with the partner 3 and the Norwegian partner 4 will provide technical support.
Activity 3 Support activities
This activity will focus on the information and promotional activities of the partners and their publishing activities towards the public and the education of the young generation. The main activities are considered to be publications on wetlands for the professional public, for students, information boards, workshops, field study stays of partner 3 students directly in wetlands, opening and closing conferences, as well as participation and presentation of project results at the scientific conference Applied Natural Sciences.
Activity Project management
The project management will be carried out by the project team. The project manager and project coordinator will be a representative of the applicant, the financial manager will be a representative of the partner 1. The other project partners will be part of the project structure as responsible activity manager and responsible task solvers. The publicity manager will be a representative of applicant.
e) Target groups and end beneficiaries:
The project will focus on the following: The general public, who will be aware of the importance of wetlands in the fight against climate change. Awareness of the possibility of solving some environmental problems with root wastewater treatment plant. Young people who will have knowledge of wetlands and biodiversity and will also gain practical experience with the implementation of measures. Academics who will be able to implement an improved curriculum for students in the field of science and ecology. A socially vulnerable group of people who will be involved in implementation work. Entrepreneurs who will be involved in ecosystem services resulting from project.
f) Partnership:
The project will be implemented in partnership: applicant Voda pre klímu - environmentálne technológie o.z. (Water for Climate - environmental technologies c.a.), partner No. 4 - from the donor country Norway - Norwegian University of Life Science, partners from the Slovak Republic Partner No. 1 Štátna ochrana prírody SR v Banskej Bystricy (State Nature Conservancy of the Slovak Republic in Banská Bystrica), Partner No.2 Základná škola s materskou školou Maximiliána Hella (Primary & Secondary School of Maximilian Helll), Partner No. 3 Univerzita sv. Cyrila a Metoda v Trnave (University of Ss. Cyril and Methodius in Trnava). The role of the partner 4 - Norwegian University of Life Science is, to pass on experience and expertise and to research the impact of the project on students and the young generation on the perception of the problem of climate change.
a) Relevant measures to be implemented:
Activity 1 consists of these tasks:
Task 1.1 Preparation of wetland revitalisation
Task 1.1.1 Detailed mapping - mapping of plant, animal species and biotope in the area of interest
Task 1.1.2 Preparation of map materials - elaboration of map materials for field work
Task 1.1.3 creation of database from mapping results (KIMS, MAPBIO) - processing of mapping results and their recording in the database (KIMS, MAPA)
Task 1.1.4 linking research results applicant, partner 3 database with partner 1 - processing of results and their interconnection
Task 1.1.5 Report interpretation of results - presentation of monitoring results to stakeholders
Task 1.2. implementation of water retention measures - building water retention measures in cooperation with local communities
Task 1.2.1 Project design preparation - elaboration of detailed project documentation for all of wetlands sites.
Task 1.2.2 Implementation in the field - construction of water retention measures, water retention dams, sedimentation and infiltration pits or dry polders; building refuges for amphibians and reptiles
Task 1.2.3 Root cleaner for wetland Gajdosovo - construction of a root treatment plant near Protected area Gajdošovo to prevent leakage of contaminated water into PR Gajdošovo
Task 1.2.4 Basic management of the wetland - ensuring appropriate management - mowing, removal of overgrown trees; ensuring grazing and removal of fallow land in the part of Protected area Gajdošovo
b) Relevant Project indicators: Improved environmental status of supported ecosystems. The estimated area of restored wetland ecosystems is 196,690 m2. The number of supported wetlands is 5 in four localities.
c) Expected timeline: Task 1.1 from 1 to 27, Task 1.2 from 1 to 31
d) Responsible entity and other entities involved:
Responsible partner for activity is the Partner 1, (Task 1.1.4 involves in addition following entities: applicant, Partner 3, Partner 4)
a) Relevant measures to be implemented:
Activity 2 consists of these tasks:
Task 2.1 Detailed monitoring by Dron - Orthophotomap, temperature map of terrain surfaces, NDVI index - photosynthesis activity. Defining micro-basins and runoff conditions in them in the monitored area Risk analysis of the vulnerability of the area from the point of view of water and heat balance will be done .
Task 2.2 Detailed analysis of water and soil - regular analysis of the water and soil samples, soil substrates and/or plants will be done in cooperation with partner 3.
Task 2.3 Monitoring net
Task 2.3.1 Detailed project design - elaboration of detailed project documentation for installation of monitoring net
Task 2.3.2 Installation and operation of the monitoring net - System of meteorological measurement consist of wind speed and direct, precipitation, radiation intensity, soil and atmosphere humidity temperature, water sampling, NDVI index, infra red of surface will be installed in each of wetland site.
b) Relevant Project indicators:
The activity is mainly fulfilled by the indicator: Improved environmental status of supported ecosystems and the number of supported wetlands in the number of 4 in four localities and ecosystem area 196,690 m2.
c) Expected timeline:
The activity will start with public procurement in 1st month and will end with the commissioning of the monitoring network in 11. This will be followed by operation and data collection from the monitoring network until 31 and subsequent operation in the sustainability of the project.
d) Responsible entity and other entities involved:
Applicant - Tasks 2.1, 2.3.1, Partner 3 - Tasks 2.2, 2.3, 2.3.1, 2.3.2
Partner 1 - Tasks 2.3.1, 2.3.2 and sustainability of the project
a) Relevant measures to be implemented: Activity 3 consists of these tasks:
Task 3.1 Awareness raising campaign of partner 2 Partner 2 will be responsible to create and open the information point of the project in the Primary and secondary school of Štiavnické Bane. The information point in Štiavnické Bane will serve to promote not only the entire project and the target wetlands, but also to inform the general public about the existence of these wetlands and their importance. This activity also includes the organization of presentations and workshops during the project and the revitalization of a wetland located on the school premises. Part of the awareness-raising campaign of partner 2 is also the elaboration of the publication of wetland for children which will be prepared, printed and distributed (4000 pcs). The school pupils will accompany visitors to the school area and promote the results of the project.
Task 3.2 Awareness raising campaign of applicant Elaboration of the physical 3D model of reconstructed wetland Michalka, establishment of the information centre for ecological education, reconstruction of the former garden into a garden with rainwater retention and the creation of a wetland, organisation of the workshops and presentations in information centre and elaboration of the publications of the reconstructed wetlands and hydrologic studies for every locality of the wetland measures. Applicant will arrange the excursions to the wetlands target areas of the project and will arrange the youth voluntary camps.
Task 3.3 Awareness raising campaign of partner 3 The course "Field Research" implemented in the new re-accredited study programme Protection and Restoration of the Environment (Bachelor study programme) and Environmental Engineering.
Task 3.4 Awareness raising campaign of partner 1 lectures and field trips for stakeholders; elementary and high school students, publication of professional articles and contributions, preparation the educational trail in Gajdošovo wetland and installation of the information boards.
Task 3.5 Awareness raising campaign of partner 4 Research on behavioral and student behavioral change in relation to climate change. Lectures and presentation of projects on the importance of reconstructed wetlands, organization of an in situ workshop associated with a visit to wetlands in Norway for partners from the Slovak Republic to exchange the experiences with keeping in wetlands.
b) Relevant Project indicators: Number of implemented awareness-raising campaigns, number of projects for cooperation with the donor partner, number of trainings co-organized by institutions from the contributing state and the recipient state, number of information activities,
c) Expected timeline: Task 3.1 from 3 to 31, Task 3.2 from 1 to 31, Task 3.3 from 7 to 26, Task 3.4 from 5 to 31, Task 3.5 from 4 to 24
d) Responsible entity and other entities involved: Applicant - Tasks 3.2.1, 3.2.2, 3.2.3 Partner 3 - Tasks 3.2.3, 3.3 Partner 1 - Tasks 3.4, 3.4.1, 3.4.2 Partner 4 Task: 3.1, 3.2.1,3.3,3.5
a) Relevant measures to be implemented:
Activity 4 consists of these tasks:
Task 4.1 Web sites promotion of the project The special web site of the project will be created and the link with the information of the project will be install on the all web sites of the members of the project consortium as well. social networks, and mass media.
Task 4.2 Opening meeting of the project - 3 days Kick off meeting will be hold in Štiavnické Bane. The scope of meeting will be introduction of the project teem management, web project portal. Last day of the kick off meeting will take introduction presentations for public.
Task 4.3 Closure meeting - 3 days Kick off meeting will be hold in Štiavnické Bane. The scope of meeting will be presentation results of the project, presentation of the final project reports, for public and media press.
Task 4.4 Presentations of the project on Applied Natural Sciences conference - scientific conferences "Applied Natural Sciences" or the workshops organized within this project as accompanying events to the mentioned scientific conferences.
b) Relevant Project indicators:
Mandatory - Number of website visitors - 1500, Mandatory - number of information activities: 3, Optional - number of media outputs 4
c) Expected timeline:
Task 4.1 From 1 to 3, Task 4.2 Month 1st, Task 4.3 Month 31, Task 4.4 From 20 to 25
d) Responsible entity and other entities involved:
Applicant - Tasks 4.1, Partner 2 - Tasks 4.2, 4.3 Partner 3 - Tasks 4.4
a) Relevant measures to be implemented:
b) Relevant Project indicators:
c) Expected timeline:
d) Responsible entity and other entities involved:
a) Relevant measures to be implemented:
b) Relevant Project indicators:
c) Expected timeline:
d) Responsible entity and other entities involved:
a) Relevant measures to be implemented:
b) Relevant Project indicators:
c) Expected timeline:
d) Responsible entity and other entities involved:
a) Relevant measures to be implemented:
b) Relevant Project indicators:
c) Expected timeline:
d) Responsible entity and other entities involved:
a) Brief history of organisation:
The Voda pre klimu - environmentalne technologie o.z. (Water for Climate - environmental technologies c.a.) was established in December 2008. Our goal is to create a broad platform for cooperation - a community of representatives of various professional profiles and the general public. The platform members look for the context of global climate change and global warming, and solutions to mitigate their impacts. Climate change doesn't know the boundaries of regions or states, nor the differences among scientific disciplines. Its consequences are felt equally for everyone. We realize that climatologists, meteorologists, farmers, water managers, foresters, architects, ecologists, educators, philosophers and historians and representatives of local governments and state bodies must also find a solution to the problem together. All of them in the joint creative discussion. There is no such field of human activity that should be left out of this process. That is why we try to recruit the broadest possible range of experts to our team. At present, our civic association already includes university teachers from the fields of natural sciences, history and archaeology, meteorology, forestry and agriculture, architecture and urbanism, public and state administration. We perceive water as an essential tool for regulating energy flows in the environment around us, and an elementary tool for revitalizing the environment, increasing biodiversity. Water is a resource of cooling environment and must work in synergy with the restoration and preservation of greenery, and at the same time in synergy with all other activities.
b) Main area of interest:
Environmental protection, protection against climate change, decontamination and remediation of polluted environment, water management, agriculture, waste management, energy, social sciences in relation to the environment, education and training in the form of lectures, courses or cooperation in the education of professionals in areas of environmental activities, publishing periodicals and non-periodical publications, organizing and participating in professional conferences in the field.
c) Experience with the implementation of similar Projects:
The civic association has already developed successfully. We have held a series of lectures and discussions for the public on climate change and possible solutions. We have published the publication: "Proposals for measures to mitigate the effects of climate change in the Trnava region". We have prepared a study: "Comprehensive water management for the village of Horné Orešany". We are currently preparing two projects for implementation: "Model of water retention measures" and "Relaxing, rain garden for the public placed in Trnava city."
Members of association are very skilled persons in preparation and implementation of different EU projects which were implemented for another institutions. Some of these projects are described in next project list:
Project of remediation of the underground repository for radioactive waste on NPP A-1 in Jaslovske Bohunice
Project of Lysimeter research station for research of radioactive soil contamination for NPP in Jaslovske Bohunice
Project of monitoring system for Regional Repository for Nuclear Waste at Mochovce
Project of Lysimeter research station for hydrology research for Slovak Academy Sciences Bratislava
Project of Lysimeter research station for agricultural research for Research Institute of Plant Production in Borovce
Project of Lysimeter research station for Mountain biology of Zilina University
Project for collection, separation and treatment of biological waste for High Tatras
Air quality improvement by using BAT technology for maintenance of local roads in the city High Tatras
d) Other important information (if relevant):
Former name of the association was: Združenie pre environmentálne biotechnológie a environmentálnu chémiu - ZEBEC, the new name of the organisation Voda pre klímu - environmentálne technológie o.z. is used from 2020.
a) Aims and target groups:
The target groups for the project communication plan are TG_general: general public, environment, men, women, media TG_policy: Policy related local and regional politicians, TG_education: students, academic researchers and students TG_business entrepreneurs and business management, TG_age from youth to seniors..
b) Strategy and content of the information and communication measures:
A separate communication strategy is prepared for each target group: publications and printed matter appropriate to the child's age will be prepared for the target group of school-age children. A popular form for children is a workshop and experiential learning, which will be the subject of special workshops. For the professional public and university students, it will be a professional publication of a professional lecture and presentation. For the media sector, will be prepared press releases and video. For the general public it will be information boards and excursions.
c) Information activities on progress, achievements and results in the Project (measured through publicity indicators set in section 3.3.3):
Within the project, 3 events will take place: opening event in first month and final event in last month and Participation in the scientific conference "(Applied Natural Sciences" between 19 and 25 months. Presentations will always be provided with the program logo in accordance with the Communication and Design manual. .
d) Measures for making information on the Project available on the web (establishment and regular update of dedicated web-site):
The applicant will create and regularly update a website on the existing website of the organization www.vodapreklimu.sk . information about the project published on this website will be published in Slovak and English. Counting traffic to the recipient's website will be done through google analytics. In addition to the described mandatory indicator, links to project information from the applicant's website will be placed on all partners' websites.
e) Billboard (if relevant in line with Annex 3 of Regulation):
Total 6 billboards will be created for the project: for each locality with a wetland, in the area of the M. Hella primary school and in Trnava at the project information center. All billboards will be implemented in accordance with the Communication and Design manual.
f) Fulfilment of publicity indicators (listed in part 3.3.3):
In accordance with the fulfilment of indicators, the project will include 8 workshops for primary school students and the general public in Trnava and at the Primary School M. Hella, 3 presentations during the Wetlands Day, World Water Day and World Earth Day.
Following publications will be prepared within the project:
For the professional public -„Mokrade kremnického a Štiavnického pohoria“ (Wetlands of the Kremnica and Štiavnica Mountains), in the number of 500 pieces.
Publication on wetlands for school-age children in the number of 4000 pieces.
4 roll ups will be processed for the localities of Banská Štiavnica, Trnava, Norway for the needs of project promotion.
A documentary video will be made about the individual localities of the wetlands.
Press releases will be issued at the beginning and end of the project. All materials will be implemented in accordance with the Communication and Design manual.
g) Fulfilment of publicity measures and publishing information (in line with the Information and Publicity Requirements according to Annex 3 to the Regulation and Communication and Design Manual, issued by the Financial Mechanism Office):
Some activities will require the following measures:
- Approval of orgán štátnej vodnej správy (the state water administration) for the construction of a root wastewater treatment plant
- Consent of stavebný úrad (the construction office) to carry out landscaping
Title deeds and cadastral map and parcel numbers for activity 1 and 2
LV - Title deeds No 1, cadastral parcel No 3685
LV - Title deeds No. 484, cadastral parcel No 498/5, 499/8
LV - Title deeds No 62, cadastral parcel No 3252
LV - Title deeds No. 937, cadastral parcel No 1312, NO 495, NO 497, NO 447
Title deeds and cadastral map and parcel numbers for activity 3
LV - Title deeds No. 2, cadastral parcel No 116/1 and 571/1
LV - Title deeds No 2257, cadastral parcel No 1423/12
Compliance with the following regulations and strategic documents of the EU and the Slovak Republic is important for the submitted project.
Directive 2000/60 / EC - establishing a framework for Community action in the field of water policy Strategy for the adaptation of the Slovak Republic to climate change approved by a resolution of the Government of the Slovak Republic 478/2018.
Act of Nature and Landscape Protection n. 543/2002
Act of Environment n.17/1992
Orientation, Principals and Priorities Water Policy in Slovakia until 2027
Updated National Biodiversity Strategy in Slovakia until 2020
Action Plan for the Implementation of Measures Resulting from the update Biodiversity Strategy until 2020
Climate change adaptation strategy of Slovakia 2018-2025
Updated Programme of the Care of Wetlands of Slovakia for 2015-2021
Action Plan for Wetlands for 2019 – 2021
Greener Slovakia, Strategy of the Environmental policy of the Slovak Republic until 2030
NATURA 2000
Agenda 2030, EU biodiversity strategy for the year 2030
2050 - Low Carbon Economy
National Action Plan for Green Public Procurement in Slovakia 2016 - 2020
Project contribution to c ross-cutting issues:
The project is in line with the principles of promoting gender equality. These principles have been applied and will be applied in setting up the research team and in accessing the users of the results and outputs of the project and the participants of the events and activities organized within the project solution. Project partners shall ensure that in the implementation of individual activities and the use of the achieved results and outputs, equal opportunities in the access and use of the infrastructure and services obtained or offered within the project solution will be apply. During the implementation of corrective field measures, members of local Roma communities will also be involved in the work. The experience from the implementation of similar activities in Slovakia is very positive. These works do not require a skilled workforce and thus provide an excellent opportunity to socialize and increase the economic income of the population. It brings a positive sense of self-realization to society. Indirectly, however, it provides an environment for improving the living conditions of all groups concerned. The project is absolutely non-discriminatory. There are no discriminatory obstacles during its preparation and implementation. All purchases will be made by public procurement with the highest degree of transparency.
The costs and sources of financing of the Project sustainability:
The costs for the sustainability of the project are linked to the maintenance of vegetation, removal of airborne vegetation and maintenance of water retention measures.
Wages and operating costs will be covered from the annual budget of the Partner 1 State Nature Conservancy of the Slovak Republic Štiavnické vrchy Protected Landscape Area Administration.
Reasons why some of the compulsory annexes are missing (if relevant):
Other information (if relevant):
Expert opinion for the price of land Gajdošovo. The best solution for implementing the plan for the Gajdošovo wetland is to buy the land into the ownership of partner 1. Even if we have the owner's consent to implement of activities. (It is attached to the project). The annex documents a contract for a future contract, which is already signed by the current owner. Due to administrative delays in connection with the COVID pandemic, the Director of Partner 1 did not have time to sign the document. We will send it immediately after signing as part of the amendment.
Also due to the COVID pandemic, an agreement on the lease of premises on Františkánská Street 1 in Trnava has not yet been signed. We will send it immediately after signing as part of the amendment.
a) Job positions within the Project responsible for Project management on the Applicant´s side:
The position of project coordinator will be represented by Ivan Matušek - certified senior project manager IPMA B, previously held the position of validator for certification of project managers in the Slovak Republic. He has 25 years of experience in creating and managing projects, project teams, especially in the field the environment. Graduate of the Faculty of Science, Comenius University in Bratislava. Ján Tóth will be the publicity manager for the applicant. He has also 20 years of experience with graphic design, web applications and the creation of graphic printing materials. Rastislav Mraz will be expert of public procurement, he is lawyer with long term experiences in public procurement.
b) Job positions within the Project responsible for Project management on the Partner´s side (if relevant):
Partner 1 will provide a financial manager to the project team: Zuzana Švantnerová, a long-term project manager of partner 1 with experience from EU projects and Norwegian funds. The project team will also include the solvers of individual activities, which will be provided by the applicant as well as all partner separately.
c) Main areas of responsibility to individual job positions within the Project:
The project manager (Ivan Matušek) is responsible for the project, the financial manager is responsible for the financial part (Zuzana Švantnerová), after signing the project contract each partner nominates a responsible accountant person to the project team who will cooperate and report to the financial manager.
d) Statutory representative of the Applicant:
The statutory representative of the applicant is Ivan Matušek chairman of the Voda pre klímu - environmentálne technológie o.z. (Water for Climate - environmental technologies c.a.)
e) Statutory representative of the Partner (if relevant):
not relevant
f) Limitations of Statutory representative of the Applicant/Partner:
Partner 1 - Directorate - General approval to be participant in the project.
Partner 3 - Rector of the university approval to be participant in the project.
g) Other relevant information on the management of the Project, if relevant:
The project will be managed through a common internet interface - the project portal created by applicant.
a) Relevance of Project activities for defined target groups:
The implementation of the project directly affects two target groups: 1. unemployed and disadvantaged citizens and citizens from Roma tribes. These groups of citizens will be involved in building water retention measures. The implementation of these works does not require a qualified workforce. Tests have already been carried out in Slovakia which have shown that under professional supervision this target group achieves excellent work results and it helps it to achieve a higher social and economic status. 2. University students. As part of the project, Partner 3 plans to carry out field research on the territory of revitalized wetlands, which will directly positively affect the quality of their education. The same assumption can be said about primary school students, especially students of the Primary & Secondary School of Maximilian Hell. Also the project has an indirect impact on the general public, in terms of improved living conditions and ecosystem services.
b) Current status of target groups:
Slovak Republic still has a high unemployment rate in the region of Central Slovakia. It mainly affects communities with a low level of education and is particularly evident in Roma communities. As a result, these citizens suffer from the effects of poor employment, alcoholism, family breakdown, low living standards and housing. Slovak universities suffer from an acute lack of funding for the implementation of interesting research activities and learning processes. It is therefore extremely important for them if they get the opportunity to carry out additional forms of study.
c) Other target groups, if relevant: entrepreneurs, small and medium-sized enterprises involved in the implementation of works, research organizations involved in research activities
What is the Partner’s technical / professional contribution to the Project implementation? Partner is fully technically and personally equipped to ensure the implementation of field work. He is the administrator of wetland sites.
What will be achieved by the partnership in relation to the Project Outcomes and Outputs? Partner is the main guarantor of the implementation of revitalization works in the wetlands.
How the partnership will facilitate the strengthening of bilateral relations? Partner plays a key role for the work, because he is also the administrator of the affected sites. Partner provided the reason for the existence of the project and thus also the partnership.
Is the partnership expected to have broader implications? Partner creates great potential and the need to solve other problems in connection with nature protection and thus also the prospect of developing relations.
What is the Partner’s technical / professional contribution to the Project implementation? Partner has extensive experience in the implementation of projects from Norwegian funds, he is the guarantor of partnership cooperation with the donor state Norway and he is professionally equipped to work with the young generation and with publicity in general.
What will be achieved by the partnership in relation to the Project Outcomes and Outputs? Partner will have a great influence on the quality of promotional and information activities, also on the making of materials for the young generation.
How the partnership will facilitate the strengthening of bilateral relations? Partner has a long tradition in bilateral relations with donor countries and thus will greatly facilitate mutual contact for the entire project team.
Is the partnership expected to have broader implications? Partner traditionally develops strong ties to the donor country.
What is the Partner’s technical / professional contribution to the Project implementation? Partner forms a scientific research base in the project team and is staffed and technically equipped to deliver the required activities..
What will be achieved by the partnership in relation to the Project Outcomes and Outputs? Execution of input analyzes and late processing of output data is of great importance in the decision-making process of measures and in documenting the results and impact of implemented measures on revitalized wetlands.
How the partnership will facilitate the strengthening of bilateral relations? Partner comes into contact with the donor state and its organizations for the first time. This project creates the preconditions for him.
Is the partnership expected to have broader implications? There is great potential and interest in developing relationships.
What is the Partner’s technical / professional contribution to the Project implementation? Partner is fully personally and technically equipped to fulfil the required goals and tasks.
What will be achieved by the partnership in relation to the Project Outcomes and Outputs? Partner has a detailed methodology for assessing the impact of the project on the behavior of the population towards climate change.
How the partnership will facilitate the strengthening of bilateral relations? Partner is already developing traditional relations with Primary & Secondary School of Maximilian Helll and this partnership created a good precondition for the cooperation of the whole team.
Is the partnership expected to have broader implications? The traditional partnership between partner and the primary school can be extended to other institutions involved in the project.

## Budget
PROJECT BUDGET - DIRECT EXPENDITURE
| Applicant: | Voda pre klímu - environmentálne technológie o.z. | [5 empty] | Direct Expenditure: | 771133
| Partner1: | Štátna ochrana prírody Slovenskej republiky | [5 empty] | Indirect Costs: | 39007
| Partner2: | Základná škola s materskou školou Maximiliána Hella | [5 empty] | Reserve: | 33000
| Partner3: | Univerzita sv. Cyrila a Metoda v Trnave | [5 empty] | In-kind contributions: | 44000
| Partner4: | Norges miljø- og biovitenskapelige universitet | [5 empty] | Total Eligible Expenditure: | 887140
| Expenditure Item | Unit | Quantity | Unit Costs | Total Amount | Type of Expenditure | Activity | Budget Heading | Incurred by | Comments | Activities Titles (helper)
1 | Project coordinator | person hour | 720 | 30 | 21600 | Cost of staff assigned to the project | Project Management | Current expenses - on staff | Applicant | Activities in the coordination of the project and the project team, operational control of the fulfillment of tasks and outputs on a daily basis, control of the fulfillment of the schedule of activities, elaboration of reports and the final report of the project. | Project Management
2 | Publicity manager | person hour | 480 | 30 | 14400 | Cost of staff assigned to the project | Project Management | Current expenses - on staff | Applicant | Activities in the operational control of the financial implementation of the project, preparation of accounting payments, control of financial documents and statements, coordination of partners' accountants. | Project Management
3 | Drone terrain mapping | person hour | 790 | 40 | 31600 | Cost of staff assigned to the project | Activity2 | Current expenses - on staff | Applicant | Detailed mapping of the surface of wetland sites in high resolution (in cm scales). Elaboration of orthophotomaps, maps of surface temperature in the infrared spectrum, scanning of NDVI indexes and execution of maps, repeated scanning at different vegetation periods, evaluation of the obtained data. 2 experts at an hourly rate of 40 €/hour. | Net monitoring
4 | Office information staff | person hour | 1200 | 25 | 30000 | Cost of staff assigned to the project | Activity3 | Current expenses - on staff | Applicant | Permanent employee of the information center. This employee will work 150 working days for 6 hours. He/She will organize all information activities concerning revetalised wetlands, prepare materials, organize the work on the implementation and operation (exhibitions and invitation for public) of the information center throughout the whole project realization. | Awareness raising campaign
5 | Purchasing office center furniture and equipment | set | 1 | 7020 | 7020 | Consumables and supplies | Activity3 | Current expenses - office equipment | Applicant | The following equipment will be purchased for the leased premises of the information center: 20 pcs of chairs, 5 pcs of armchairs, technical table, hangers, blinds and shutters, conference table, 4 pcs of shelf cabinets, 3 pcs of lockable shelf cabinets, canvas 150", flipchart, BT speaker with battery, cabling, 1 pc. notebook, 1 pc. dataprojector, wall holder for projector-for projection, presentation and administration of the activities at the information center, 1 pc multifunctional color printer for the purpose of printing monitoring reports of project documentation, copying and scanning documents for project administration. Discussions, seminars and screenings of presentations and video projections on revitalized wetlands will be organized in this info center. | Awareness raising campaign
6 | Construction of a rain garden | set | 1 | 28100 | 28100 | Costs entailed by other contracts | Activity3 | Investment costs - Infrastructure | Applicant | Reconstruction of the former garden into a garden with rainwater retention and the creation of a wetland in the building at Františkánská Street 1 in Trnava, as a branch of the information center. Including excavation work, installation of rainwater runoff to capture rainwater from the roofs of surrounding buildings, construction of rainwater distribution, landscaping and planting. Including the purchase of materials, externally contracted deliveries of machine excavations, externally contracted professional supervision services, including the work of volunteers on landscaping, installation and planting. In the revitalized garden we will show the functions of wetlands revitalized within the project. | Awareness raising campaign
7 | Lecturers Trnava | person hour | 630 | 40 | 25200 | Cost of staff assigned to the project | Activity3 | Current expenses - on staff | Applicant | : Lectures and presentations of experts in the position of lecturers during information activities in the information center in Trnava, where experts will educate the public in Trnava about the need for wetlands and present its effect on climate change on the example of wetlands revitalized within the project. 20 information days + 2 days for preparation of lectures for 4 experts in the position of lecturers. | Awareness raising campaign
8 | Production of 3D model of water retention measures - material | set | 1 | 2200 | 2200 | Consumables and supplies | Activity3 | Current expenses - purchase of material | Applicant | Purchase of materials needed for the production of the model: console, modeling materials, paints, wood, hose pipes and others. The model will be an exact copy of the revitalized Wetland Michálka. | Awareness raising campaign
9 | Production of 3D model of water retention measures - staff expenses | person hour | 250 | 25 | 6250 | Cost of staff assigned to the project | Activity3 | Current expenses - on staff | Applicant | Working time in the production of the model, processing of materials and assembly of the model, production and assembly of model parts, 3 workers. | Awareness raising campaign
10 | Workshop with 3D Model of water retention system | person hour | 80 | 40 | 3200 | Cost of staff assigned to the project | Activity3 | Current expenses - on staff | Applicant | Realisation of workshops by professional staff, experts and clarifying of the function of water retention measures in the environment for the revitalization of wetlands in the project, the positive impact of wetlands and implemented measures on groundwater levels, flood effects, climate change mitigation, environmental impact on the microclimate. A total of 8 working days for the implementation and preparation of workshops. | Awareness raising campaign
11 | Excursion to wetland sites from Trnava | set | 2 | 1100 | 2200 | Cost of staff assigned to the project | Activity3 | Current expenses - propagation and dissemination | Applicant | Organization of 2 excursions from Trnava to wetland sites defined in the project. Contractually purchased a bus for 40 persons, wage of a lecturer - expert when accompanied during the excursion, 8 hours for one excursion, refreshments for participants of the excursions. | Awareness raising campaign
12 | Travel cost to Norway | set | 1 | 17940 | 17940 | Travel and subsistence allowances for staff | Activity3 | Current expenses - travel | Applicant | Flat rate costs for a trip to Norway for a workshop on wetlands, for 12 participants and for 5 days, 12 flight tickets Norway-Slovakia. | Awareness raising campaign
13 | Travel in Slovakia | set | 1 | 846 | 846 | Travel and subsistence allowances for staff | Activity3 | Current expenses - travel | Applicant | 18 trips between Trnava and Štiavnické Bane (160 km distance) for the needs of the transport of materials and equipment for information activities, organization of information activities in Štiavnické Bane, control of the state of field work on wetland localities, subsistence allowances 9 persons/30 days. | Awareness raising campaign
14 | Elaboration of publications on wetlands | person hour | 220 | 40 | 8800 | Cost of staff assigned to the project | Activity3 | Current expenses - propagation and dissemination | Applicant | Elaboration of a specialized publication (approx. 20 pages) on the impact of wetlands on climate change mitigation in the given localities and their impact on the local microclimate. 4 authors - experts for 50 hours. | Awareness raising campaign
15 | Elaboration of hydrology studies | person hour | 850 | 40 | 34000 | Cost of staff assigned to the project | Activity3 | Current expenses - on staff | Applicant | Elaboration of 4 professional hydrological studies with a proposal of measures and the method of implementation of landscape management. For each locality wetlands separately, Michalka, Gajdošovo, Kopernica, Bartošovo. | Awareness raising campaign
16 | Publication printing | pc. | 500 | 3 | 1500 | Costs entailed by other contracts | Activity3 | Current expenses - propagation and dissemination | Applicant | Print of the publication on wetlands: The subject of the contract is the production and design of the publication, 20 pages, print 4/4, 130 g ONM, binding V1, cover 250 g ONM, 4/4. | Awareness raising campaign
17 | Financial manager | person hour | 960 | 17 | 16320 | Cost of staff assigned to the project | Project Management | Current expenses - on staff | Partner1 | Activities in the operational control of the financial implementation of the project, preparation of accounting payments, control of financial documents and statements, coordination of partners' accountants. | Project Management
18 | Land Gajdošovo | set | 1 | 22500 | 22500 | Land and real estate | Activity1 | Investment costs - Infrastructure | Partner1 | Purchase of land in the fourth degree of protection, is important to ensure the long-term systematic care of several rare and endangered species of flora. | Wetland revitalization
19 | Revitalization land Gajdošovo | set | 1 | 50946 | 50946 | Costs entailed by other contracts | Activity1 | Investment costs - Infrastructure | Partner1 | Cutting of overgrown trees, milling of stumps after production on an area of 3.6 ha. | Wetland revitalization
20 | Detailed mapping of the wetland sites | person hour | 1640 | 15 | 24600 | Cost of staff assigned to the project | Activity1 | Current expenses - on staff | Partner1 | Detailed mapping 1 growing season, Kopernica 384 hours, Bartoška 384 hours, Michalka 256 hours, Gajdošovo 640 hours. | Wetland revitalization
21 | Water retention measures Bartošovo, Kopernica, Michalka, Gajdošovo | set | 1 | 51300 | 51300 | Costs entailed by other contracts | Activity1 | Investment costs - Infrastructure | Partner1 | 77 pcs of water retention devices (wooden thresholds, steps, partitions), diversion of polluted water out of the wetland, 1 bentonite dam, 10 pcs seepage pits, road bridging, technical intervention to flood meadows. | Wetland revitalization
22 | Evaluation and data processing from monitoring net | person hour | 625 | 40 | 25000 | Cost of staff assigned to the project | Activity1 | Current expenses - on staff | Partner1 | Filling KIMS databases, production of current GIS layers and maps. | Wetland revitalization
23 | Land management Bartošovo, Kopernica, Michalka, Gajdošovo | set | 1 | 37100 | 37100 | Costs entailed by other contracts | Activity1 | Investment costs - Other assets | Partner1 | Twice a year for three years manual removal of overgrown trees, once a year for three years mowing and removal of biomass, once a year for three years manual cleaning of areas after removal of overgrown trees, technical intervention to flood meadows. | Wetland revitalization
24 | Monitoring net | set | 1 | 137400 | 137400 | Cost of new or second hand equipment | Activity2 | Investment costs - Equipment | Partner1 | Monitoring net will serve for complex ecosystem data obtaining for each wetland sites. The system consist of: soil moisture, temperature, and conductivity probes 15 pcs (2000 € unit price), water level probes 6 pcs (1500 € unit price), meteostations 4 pcs (17 000 € unit price), tensiometer 1 pc (700 € unit price), suction probes for soil water sampling 12 pcs (2OO€ unit price), web cameras 8 pcs 600 € unit price), Infrared sensors 7 pcs (900 € unit price), NDVI sensors 7 pcs (600 € unit price) including the protection defends on monitoring point areas, fencing (total price 12 000 €). | Net monitoring
25 | Travel | set | 1 | 3866 | 3866 | Travel and subsistence allowances for staff | Activity1 | Current expenses - travel | Partner1 | Subsistence allowances 2 persons/twice a week, fuel, control of the state of field work on wetland localities. | Wetland revitalization
26 | Educational trail | pc. | 4 | 800 | 3200 | Costs entailed by other contracts | Activity3 | Current expenses - propagation and dissemination | Partner1 | 4 pcs of educational blackboards 1.7 x 2.5 m, graphic design, production, transportation, installation on site. | Awareness raising campaign
27 | Equipments for wetland sites mapping | set | 1 | 5200 | 5200 | Consumables and supplies | Activity1 | Current expenses - office equipment | Partner1 | Notebook 1 pc, computer 1 pc (data collection from 4 monitoring nets online), 1 pc macro lens camera, 1 pc telephotocamera (determination of plants, mosses, invertebrates). | Wetland revitalization
28 | Information point building | set | 1 | 42000 | 42000 | Costs entailed by other contracts | Activity3 | Investment costs - Infrastructure | Partner2 | Waste disposal, reconstruction of electrical wiring, lighting, installation of the sound system, and repair of the floor and the wall screeds and ceiling. Furniture to ensure the functionality of the Info room. The room will be provided free of charge by the school to ensure project activities implementation. The room will be purposefully re-used for the promotion and dissemination of project outputs even after the end of the project at the expense of the school. | Awareness raising campaign
29 | Revitalization of the wetland | set | 1 | 7000 | 7000 | Costs entailed by other contracts | Activity3 | Investment costs - Other assets | Partner2 | The revitalization of the wetland consist of the exchange of soil, the planting of suitable wetland plants and the extension of water retention measures. Total area is 20 m2. Part of there revitalization of the wetland at the Primary and Secondary school of Maximilian Hell will also include the installation of information boardsshowing the importance of wetlands in nature. | Awareness raising campaign
30 | Elaboration of the wetland publication for children | set | 1 | 6500 | 6500 | Cost of staff assigned to the project | Activity3 | Current expenses - propagation and dissemination | Partner2 | Work on texts&images for the 20 pages of publication. | Awareness raising campaign
31 | Elaboration of the wetland publication for children | set | 1 | 6000 | 6000 | Costs entailed by other contracts | Activity3 | Current expenses - propagation and dissemination | Partner2 | Printing costs for 20 B5 sized pages & graphic adjustments. | Awareness raising campaign
32 | Organisation of the educational and information activities | set | 1 | 4000 | 4000 | Cost of staff assigned to the project | Activity4 | Current expenses - propagation and dissemination | Partner2 | Complete work on educational activities at Wetland Inforpoint. | Publicity and Communication
33 | Opening and closing meeting | set | 2 | 4500 | 9000 | Costs arising from project contract | Activity4 | Current expenses - mandatory publicity | Partner2 | Organisation of 2 two-days meetings for 300 people (600 together). | Publicity and Communication
34 | Project management | person hour | 300 | 15 | 4500 | Cost of staff assigned to the project | Project Management | Current expenses - on staff | Partner3 | The employee will be responsible for project management at partner No. 3, coordination of project management with the applicant (lead project manager), the process of procuring the necessary laboratory accessories and chemicals, economic-administrative tasks related to the project solution, communication between partners and control of compliance with the project solution schedule and fulfillment of project outputs. | Project Management
35 | Chemical analysis of the water and soil quality in the wetlands sites | person hour | 1000 | 18 | 18000 | Cost of staff assigned to the project | Activity2 | Current expenses - on staff | Partner3 | Within the whole realization of the project, Partner 3 will perform analyzes of water quality, soil for the presence of contaminants, and possible environmental toxicity for wetlands of the project sites at its laboratories. Costs are quantified in the form of personnel costs related to sampling, samples treatment and their analysis. During the solution of the project, the collection and processing of min. 500 samples will be recorded. | Net monitoring
36 | Purchasing of the chemicals and consumable material | set | 1 | 11500 | 11500 | Consumables and supplies | Activity2 | Current expenses - purchase of material | Partner3 | Purchase of chemicals and laboratory expendable supplies for realization of water and soil analyzes. | Net monitoring
37 | Field research with bachelors students | set | 3 | 4700 | 14100 | Cost of staff assigned to the project | Activity3 | Current expenses - propagation and dissemination | Partner3 | Within this task, there 3 research trips - 5 days/trip and min. 10 participants/trip are planned. Costs will include travel, accommodation and diet. Within this course, students of the bachelor and engineering study program complete their Field Research focused on the collection of water and soil substrates samples, as well as plants occurring within the studied area of wetlands. They will also carry out in-situ measurements. | Awareness raising campaign
38 | Participation in the conference and organization of the workshop | person hour | 135 | 40 | 5400 | Cost of staff assigned to the project | Activity4 | Current expenses - propagation and dissemination | Partner3 | The results and outputs of the project (especially scientific) will be presented through the active participation on the scientific events organized by UCM in Trnava - scientific conferences "Applied Natural Sciences" and on the workshops organized within this project as accompanying events to the mentioned scientific conferences. The expenses include preparation and organisation of participation on conference and preparation of presentation and scientific articles to be published, 3 experts. | Publicity and Communication
39 | Expert Norway 1 | person hour | 326 | 45 | 14670 | Cost of staff assigned to the project | Activity3 | Current expenses - on staff | Partner4 | Research activities, preparation of workshops in Norway and Slovakia, presentations, conference participations. | Awareness raising campaign
40 | Expert Norway 2 | person hour | 326 | 25 | 8150 | Cost of staff assigned to the project | Activity3 | Current expenses - on staff | Partner4 | Research activities, preparation of workshops in Norway and Slovakia, presentations, conference participations. | Awareness raising campaign
41 | Workshop Norway | set | 1 | 2180 | 2180 | Costs arising from project contract | Activity3 | Current expenses - propagation and dissemination | Partner4 | Preparation and organisation of workshop 12 hours, refreshment for 10 people and lunch for 12 people, transport to the wetland area. | Awareness raising campaign
42 | Travel 4 times from Norway to Slovakia | set | 1 | 5115 | 5115 | Travel and subsistence allowances for staff | Activity3 | Current expenses - travel | Partner4 | 2 persons, travel costs, 3 visits for 2 nights. | Awareness raising campaign
43 | Equipment for research | set | 1 | 660 | 660 | Consumables and supplies | Activity3 | Current expenses - other | Partner4 | Headcameras 2 pcs, Audio Recorder X4 1 pc. | Awareness raising campaign
44 | Leaflets | set | 1 | 70 | 70 | Consumables and supplies | Activity3 | Current expenses - propagation and dissemination | Partner4 | Elaboration and printing of information leaflets. | Awareness raising campaign
45 |  |  |  |  | 0
46 |  |  |  |  | 0
47 |  |  |  |  | 0
48 |  |  |  |  | 0
49 |  |  |  |  | 0
50 |  |  |  |  | 0
51 |  |  |  |  | 0
52 |  |  |  |  | 0
53 |  |  |  |  | 0
54 |  |  |  |  | 0
55 |  |  |  |  | 0
56 |  |  |  |  | 0
57 |  |  |  |  | 0
58 |  |  |  |  | 0
59 |  |  |  |  | 0
60 |  |  |  |  | 0
61 |  |  |  |  | 0
62 |  |  |  |  | 0
63 |  |  |  |  | 0
64 |  |  |  |  | 0
65 |  |  |  |  | 0
66 |  |  |  |  | 0
67 |  |  |  |  | 0
68 |  |  |  |  | 0
69 |  |  |  |  | 0
70 |  |  |  |  | 0
71 |  |  |  |  | 0
72 |  |  |  |  | 0
73 |  |  |  |  | 0
74 |  |  |  |  | 0
75 |  |  |  |  | 0
76 |  |  |  |  | 0
77 |  |  |  |  | 0
78 |  |  |  |  | 0
79 |  |  |  |  | 0
80 |  |  |  |  | 0
81 |  |  |  |  | 0
82 |  |  |  |  | 0
83 |  |  |  |  | 0
84 |  |  |  |  | 0
85 |  |  |  |  | 0
86 |  |  |  |  | 0
87 |  |  |  |  | 0
88 |  |  |  |  | 0
89 |  |  |  |  | 0
90 |  |  |  |  | 0
91 |  |  |  |  | 0
92 |  |  |  |  | 0
93 |  |  |  |  | 0
94 |  |  |  |  | 0
95 |  |  |  |  | 0
96 |  |  |  |  | 0
97 |  |  |  |  | 0
98 |  |  |  |  | 0
99 |  |  |  |  | 0
100 |  |  |  |  | 0

## Nepriame výdavky (hidden)
| Žiadateľ | Partner1 | Partner2 | Partner3 | Partner4
| 21600 | 16320 | 6500 | 4500 | 14670
| 14400 | 24600 | 4000 | 18000 | 8150
| 31600 | 25000 | 10500 | 14100 | 22820
| 30000 | 65920 | 1575 | 5400
| 25200 | 9888 |  | 42000 |  | 318490
6250
3200
2200
8800
34000
15% | 177250
26587.5

## Overview
Project Outputs | [6 empty] | Related costs (automatic) | % on Total Eligible Expenditure
Project Management | Project Management | [5 empty] | 56820 | 6.405%
Output1 | Restoration of degraded wetland ecosystems | [5 empty] | 714313 | 80.52%
Output2 | #REF! | [5 empty] | 0 | 0%
Output3 | #REF! | [5 empty] | 0 | 0%
[6 empty] | DIRECT EXPENDITURE | 771133
[6 empty] | INDIRECT COSTS | 39007
[6 empty] | RESERVE | 33000
[6 empty] | IN-KIND CONTRIBUTIONS | 44000
[6 empty] | TOTAL ELIGIBLE EXPENDITURE | 887140 | Warning - not all activities has been assigned to outputs! Check rows 20 - 28, column G!
Project Activities | [5 empty] | Relates to output No | Related costs (automatic) | % on Total Eligible Expenditure | Activities - filtered
Project Management | Project Management |  |  |  | Project Management |  | 56820 | 6.405% | Project Management
Activity1 | Wetland revitalization |  |  |  | Restoration of degraded wetland ecosystems |  | 220512 | 24.86% | Activity1
Activity2 | Net monitoring |  |  |  | Restoration of degraded wetland ecosystems |  | 198500 | 22.38% | Activity2
Activity3 | Awareness raising campaign |  |  |  | Restoration of degraded wetland ecosystems |  | 276901 | 31.21% | Activity3
Activity4 | Publicity and Communication |  |  |  | Restoration of degraded wetland ecosystems |  | 18400 | 2.074% | Activity4
Activity5 |  |  |  |  | Restoration of degraded wetland ecosystems |  | 0 | 0%
Activity6 |  |  |  |  | Restoration of degraded wetland ecosystems |  | 0 | 0%
Activity7 |  |  |  |  | Restoration of degraded wetland ecosystems |  | 0 | 0%
Activity8 |  |  |  |  | Restoration of degraded wetland ecosystems |  | 0 | 0%
[6 empty] | DIRECT EXPENDITURE | 771133
[6 empty] | INDIRECT COSTS | 39007
[6 empty] | RESERVE | 33000
[6 empty] | IN-KIND CONTRIBUTIONS | 44000
[6 empty] | TOTAL ELIGIBLE EXPENDITURE | 887140 | Warning - not all budget items has been assigned to activities. Check column G in the budget!
Project Budget by Budget Headings | [6 empty] | Related costs (automatic) | % on Total Eligible Expenditure | Infrastructure (Investment costs+reserve) | Non-investment costs (current costs + indirect costs + in-kind)
Chapter1 | Investment costs - Infrastructure |  |  | Construction works |  |  | 194846 | 22% | 409346 | 477794
Chapter2 | Investment costs - Equipment |  |  | Equipment |  |  | 137400 | 15% | 46% | 54%
Chapter3 | Investment costs - Other assets |  |  | Intangible Assets |  |  | 44100 | 5%
Chapter4 | Current expenses - on staff |  |  | Staff |  |  | 277490 | 31%
Chapter5 | Current expenses - mandatory publicity |  |  | Mandatory publicity |  |  | 9000 | 1.014%
Chapter6 | Current expenses - propagation and dissemination |  |  | Extra publicity |  |  | 53950 | 6.081%
Chapter7 | Current expenses - purchase of material |  |  | Material |  |  | 13700 | 2%
Chapter8 | Current expenses - travel |  |  | Travel |  |  | 27767 | 3.13%
Chapter9 | Current expenses - office equipment |  |  | Office equipment |  |  | 12220 | 1%
Chapter10 | Current expenses - running costs |  |  | Running costs |  |  | 0 | 0%
Chapter11 | Current expenses - depreciation |  |  | Depreciation |  |  | 0 | 0%
Chapter12 | Current expenses - other |  |  | Other |  |  | 660 | 0%
[6 empty] | DIRECT EXPENDITURE | 771133
[6 empty] | INDIRECT COSTS | 39007
[6 empty] | RESERVE | 33000
[6 empty] | IN-KIND CONTRIBUTIONS | 44000
[6 empty] | TOTAL ELIGIBLE EXPENDITURE | 887140 | Warning - not all budget items has been assigned to budget headings. Check column I in the budget!
Project Budget by Entities and Activities
Entity |  | Applicant | Partner1 | Partner2 | Partner3 | Partner4 | TOTAL | % of DIRECT EXPENDITURE
Activity |  | Voda pre klímu - environmentálne technológie o.z. | Štátna ochrana prírody Slovenskej republiky | Základná škola s materskou školou Maximiliána Hella | Univerzita sv. Cyrila a Metoda v Trnave | Norges miljø- og biovitenskapelige universitet
Project Management | Project Management | 36000 | 16320 | 0 | 4500 | 0 | 56820 | 7.368%
Wetland revitalization | Activity1 | 0 | 220512 | 0 | 0 | 0 | 220512 | 28.6%
Net monitoring | Activity2 | 31600 | 137400 | 0 | 29500 | 0 | 198500 | 25.74%
Awareness raising campaign | Activity3 | 167256 | 3200 | 61500 | 14100 | 30845 | 276901 | 35.91%
Publicity and Communication | Activity4 | 0 | 0 | 13000 | 5400 | 0 | 18400 | 2.386%
| Activity5 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Activity6 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Activity7 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Activity8 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| TOTAL | 234856 | 377432 | 74500 | 53500 | 30845 | 771133
Output / Activity | Project Management | Activity1 | Activity2 | Activity3 | Activity4 | Activity5 | Activity6 | Activity7 | Activity8 | TOTAL ELIGIBLE COSTS BY TYPES OF EXPENDITURE | % of TOTAL ELIGIBLE EXPENDITURE
Type of Expenditure | Project Management | Wetland revitalization | Net monitoring | Awareness raising campaign | Publicity and Communication
Cost of staff assigned to the project | 56820 | 49600 | 49600 | 153070 | 9400 | 0 | 0 | 0 | 0 | 318490 | 35.9%
Travel and subsistence allowances for staff | 0 | 3866 | 0 | 23901 | 0 | 0 | 0 | 0 | 0 | 27767 | 3.13%
Cost of new or second hand equipment | 0 | 0 | 137400 | 0 | 0 | 0 | 0 | 0 | 0 | 137400 | 15.49%
Land and real estate | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22500 | 2.536%
Consumables and supplies | 0 | 5200 | 11500 | 9950 | 0 | 0 | 0 | 0 | 0 | 26650 | 3.004%
Costs entailed by other contracts | 0 | 139346 | 0 | 87800 | 0 | 0 | 0 | 0 | 0 | 227146 | 25.6%
Costs arising from project contract | 0 | 0 | 0 | 2180 | 9000 | 0 | 0 | 0 | 0 | 11180 | 1.26%
INDIRECT COSTS - Reg. Art. 8.5 | [9 empty] | 39007 | 4.397%
RESERVE - Reg. Art. 7.6.3.k) | [9 empty] | 33000 | 3.72%
IN-KIND CONTRIBUTIONS - Reg. Art. 6.4.5 | [9 empty] | 44000 | 4.96%
TOTAL ELIGIBLE COSTS | 56820 | 220512 | 198500 | 276901 | 18400 | 0 | 0 | 0 | 0 | 887140
% TOTAL COSTS | 6.405% | 24.86% | 22.38% | 31.21% | 2.074% | 0% | 0% | 0% | 0% | 100%
TOP TEN BIGGEST EXPENDITURE ITEMS | Amount | % on total eligible expenditure
Monitoring net | 137400 | 15.49%
Water retention measures Bartošovo, Kopernica, Michalka, Gajdošovo | 51300 | 5.783%
Revitalization land Gajdošovo | 50946 | 5.743%
Information point building | 42000 | 4.734%
Land management Bartošovo, Kopernica, Michalka, Gajdošovo | 37100 | 4.182%
Elaboration of hydrology studies | 34000 | 3.833%
Drone terrain mapping | 31600 | 3.562%
Office information staff | 30000 | 3.382%
Construction of a rain garden | 28100 | 3.167%
Lecturers Trnava | 25200 | 2.841%
Expected schedule
Milestone | Started | Duration
Opening meeting | 1 | 2
Project detailed design of net monitoring | 1 | 2
Preparation of 3D model | 1 | 5
Web sites promotion of the project | 1 | 5
Detail design documentation of Information point Trnava | 1 | 5
Project detail design documentation of wetlands measures | 1 | 5
Finish of procurement | 1 | 5
Popular publication of wetland general | 1 | 11
Opening of Information point Stiavnicke bane | 1 | 11
Installation and start of operation of monitoring net | 1 | 11
Opening of Information point Trnava | 1 | 11
Initial treatment of wetland Gajdosovo finished | 1 | 17
Educational trail wetland Gajdosovo | 6 | 12
Publication Wetlands for children | 1 | 17
Preparation and installation of information boards | 6 | 12
Hydrologic studies finished | 1 | 17
Water retention measures finished | 6 | 18
Report of research on behavioral and student behavioral change | 6 | 18
Presentation of the project on on Applied Natural Sciences conference | 24 | 12
Report interpretation of results of research | 6 | 30
Final web sites promotion | 12 | 24
Closure meeting | 24 | 12
Project final report | 24 | 12
Project final financial report | 24 | 12
Project final publicity report | 24 | 12
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0

## Lists (hidden)
Region | Abbreviation | District | Sector | Abbreviation | Abbreviation2 | Specification | Slovak specification | Grant rate | Information source | Project sector | Sector | Specification | Code | Type of indicator | Indicator level | Type of expenditures | Budget heading | Subjects | Countries | Yes/No | Financing | Partnership status | Policy markers | Target group | Abbreviation | Target group | Intermediary | End beneficiary | program | Abbreviation | Abbreviation | Outcomes | Abbreviations | Abbreviations2 | Abbreviations3 | Outputs | Indicators | Level | Type | Code | Unit of measurement | Source of verification | Frequency of reporting | Baseline value | Baseline year | Target value | Publicity indicators | Specific indicators | Code | Risk type | Risk likelihood | Risk impact | Response to risk | Risk variations | Risk score | Milestone classification | Milestone significance | Milestones - deadlines | Calls | Minimum grant rate | Maximum grant rate | Indirect expenditures - method | Type of research | Academic area | Abbreviations | Disciplines | Standar choice yes/no | In-kind max
Banskobystrický | SGBB | Banskobystrický | Public Sector | Public | Public1 | Public | Public1 |  | minzp.sk/eea / minzp.sk/en/eeagrants/eea-norway-grants/ | Education | Education | Education |  | Standard | Outcome | Cost of staff assigned to the project | Investment costs - Infrastructure | Applicant | Slovakia | Yes | Advance payments | Partnership Agreement signed | Non-applicable | Age-related | TG_age | TG_age |  |  | Climate Change Mitigation and Adaptation | ACC | outcomes_ACC | outcomes_ACC |  |  |  | ACC_OTC1 | indicators_ACC_OTC1 | [9 empty] | Number of information events | Number of open access education materials |  | Programmatic | Very unlikely | Minimal | Avoid / terminate | Very unlikely_Minimal | 1 | Procurement-related | Fundamental | within 1 months | ACC01 | 500000 | 1400000 | Article 8.5.1c) | Basic research | 1 Natural Sciences | natural_sciences_fields | natural_sciences_fields | Yes | 50%
Bratislavský | SGBA | Banská Bystrica | Not-for-profit Sector | Nonprofit | Nonprofit1 | Government | State budgetary or allowance organisation | 100% | eeagrants.sk/norwaygrants.sk | Health | Health | Education policy and administrative management | 1111000 | Project | Output | Travel and subsistence allowances for staff | Investment costs - Equipment | Partner1 | Norway | No | Reimbursement | Partnership Statement signed | Relevant | Business-related | TG_business | Children and Youth (0-17) |  | x |  |  |  | Increased climate change resilience and responsiveness within targeted areas | ACC_OTC1 | indicators_ACC_OTC1 | indicators_ACC_OTC1_table | Action plans for mitigation and adaptation implemented by local authorities in urban areas | Estimated annual CO2 emissions reductions of supported entities (in tonnes) | Outcome | Binding | ACC_OTC1_IND1 | Annual number | Energy audit reports, Energy certificates | Annually (APR) | 0 | N/A | 25000 | Number of participants at information events |  |  | Operational | Unlikely | Moderate | Transfer / share | Very unlikely_Moderate | 1.41 | Publicity-related | Essential | within 3 months | ACC02 | 500000 | 1400000 | Article 8.5.1a) | Applied research | 2 Engineering and Technology | engineering_field | 1.1 Mathematics
Košický | SGKE | Banská Štiavnica | Private Sector | Private | Private1 | Regional authority | Self-governing region | 95% | eeagrants.org | Government and Civil Society | Government | Education facilities and training | 1112000 | Bilateral |  | Cost of new or second hand equipment | Investment costs - Other assets | Partner2 | Iceland |  |  | Exchange of letters/emails | Fundamental | Culture-related | TG_culture | Young adults (18-29) |  | x |  |  |  | Enhanced ability of targeted ecosystems to adapt to climate change | ACC_OTC2 | indicators_ACC_OTC2 | indicators_ACC_OTC2_table | Awareness raising activities on climate change mitigation and adaptation carried out by schools | Number of people selfreporting having more climate friendly behaviour | Outcome | Reported | ACC_OTC1_IND2 | Number | Number | 2021, 2025 | 0 | N/A | 15000 | Number of website visits |  |  |  | Likely | Serious | Mitigate | Very unlikely_Serious | 1.73 | Permits-related | Relevant | within 6 months | ACC03 | 20000 | 50000 | Article 8.5.1b) |  | 3 Medical and Health Sciences | medical_fields | 1.2 Computer and information sciences
Nitriansky | SGNR | Brezno | Inter-Governmental Sector | Intergov | Intergov1 | Local authority | Budgetary or allowance organisation of self-governing region | 95% | Facebook fun page | Social Infrastructure and Services | Social_Infrastructure | Education sector staff training | 1118100 |  |  | Land and real estate | Current expenses - on staff | Partner3 | Liechtenstein |  |  | Other formal agreements |  | Education/ research-related | TG_education | Elderly (65+) |  | x |  |  |  | Enhanced collaboration between Beneficiary and Donor State entities involved in the programme | ACC_OTCB | indicators_ACC_OTC_bilateral | indicators_ACC_OTCB_table | Awareness raising activities on climate change mitigation and adaptation carried out | Share of Slovak population benefiting from living in more climate change resilient and responsive urban areas | Outcome | Reported | ACC_OTC1_IND3 | Percentage | Statistical data (Statistical Office of the Slovak Republic) | 2021, 2025 | 0 | N/A | 10.5 | Number of presentations of the Project on other events, publications about the Project |  |  |  | Almost certain | Very serious | Accept | Very unlikely_Very serious | 2 | Services-related |  | within 12 months | ACC04 | 200000 | 1000000 | Article 8.5.1d) |  | 4 Agricultural Sciences | agriculture_fields | 1.3 Physical sciences
Prešovský | SGPO | Detva |  |  |  | Public-Private organisation | Municipality | 95% | print media | Energy | Energy | Primary education | 1122000 |  |  | Consumables and supplies | Current expenses - mandatory publicity | Partner4 | Ukraine |  |  | No formal agreement as yet |  | Health-related | TG_health | TG_business | [9 empty] | Climate change and environment education centre in Dropie supported for additional demonstration measures and educational programmes | Number of action plans completed | Output | Binding | ACC_OTC1_OTP1_IND1 | Number | Project Promoters´ records, Audio/video/print | Semi-annually | 0 | N/A | 7 | Number of promotional material produced within Project | [6 empty] | Unlikely_Minimal | 1.41 | Others |  | within 18 months | ACC05 | 200000 | 50000 | Article 8.5.1e) |  | 5 Social Sciences | social_fields | 1.4 Chemical sciences
Trenčiansky | SGTN | Krupina |  |  |  | Other public organisation | Budgetary or allowance organisation of municipality | 95% | conference/workshop | Business and Innovation | Business | Basic skills for youth and/or adults | 1123000 |  |  | Costs entailed by other contracts | Current expenses - propagation and dissemination |  | Czech Republic |  |  |  |  | Justice/home affairs-related | TG_justice | Entrepreneurs |  | x | [7 empty] | ACC_OTC2 | Number of climate change mitigation and adaptation measures implemented | Output | Binding | ACC_OTC1_OTP1_IND2 | Number | Project Promoters´ records, Audio/video/print | Semi-annually | 0 | N/A | 112 | Number of media outputs | [6 empty] | Unlikely_Moderate | 2 |  |  | within 24 months | PdP | 0 | 1200000 |  |  | 6 Humanities | humanities_fields | 1.5 Earth and related environmental sciences
Trnavský | SGTT | Lučenec |  |  |  | Intergov | Other state institution | 95% | other | Environment and Climate Change | Environment | Primary education equivalent for adults | 1123200 |  |  | Costs arising from project contract | Current expenses - purchase of material |  | - - - - - - - - - - - - - - - - - - - - - - - |  |  |  |  | Migration-related | TG_migration | SMEs (Small and Medium Sized Enterprises with 10-249 staff) | x | x | [7 empty] | Restoration of degraded wetland ecosystems | Number of physical climate change responsive measures carried out in schools | Output | Binding | ACC_OTC1_OTP2_IND1 | Number | Project Promoters´ records, Audio/video/print | Semi-annually | 0 | N/A | 80 | [7 empty] | Unlikely_Serious | 2.45 |  |  | within 36 months | [7 empty] | 1.6 Biological sciences
Žilinský | SGZA | Poltár |  |  |  | Inter-Governmental organisation | Other institution of self-government | 95% |  | Other Multisector | Multisector | Early childhood education | 1124000 |  |  |  | Current expenses - travel |  | Belgium |  |  |  |  | Minority status-related | TG_minority | Large Enterprises | x | [8 empty] | ACC_OTCB | Number of schools carrying out awareness raising campaigns | Output | Binding | ACC_OTC1_OTP2_IND2 | Number | Project Promoters’ records, Audio/video/print material | Semi-annually | 0 | N/A | 29 | [7 empty] | Unlikely_Very serious | 2.83 |  |  | within 48 months | [7 empty] | 1.7 Other natural sciences
|  | Revúca |  |  |  | Nonprofit | Intergov1 |  |  | Migration and Asylum | Migration | Secondary education | 1132000 |  |  |  | Current expenses - office equipment |  | Bulgaria |  |  |  |  | Policy-related | TG_policy | TG_culture | [9 empty] | Cooperation between Donor and Beneficiary State entities supported | Number of students participating in awareness raising campaign | Output | Binding | ACC_OTC1_OTP2_IND3 | Number | Project Promoters´ records, list of participants | Semi-annually | 0 | N/A | 7300 | [7 empty] | Likely_Minimal | 1.73 | [10 empty] | engineering_field
|  | Rimavská Sobota |  |  |  | Non-Governmental organisation (NGO) | Inter-Governmental organisation | 85% |  |  |  | Vocational training | 1133000 |  |  |  | Current expenses - running costs |  | Denmark |  |  |  |  | Work-related | TG_work | Artists |  | x | [8 empty] | Number of attendees reached by the campaigns | Output | Binding | ACC_OTC1_OTP3_IND1 | Number | Project Promoters´ records | Semi-annually | 0 | N/A | 4500 | [7 empty] | Likely_Moderate | 2.45 | [10 empty] | 2.1 Civil engineering
|  | Veľký Krtíš |  |  |  | Social Partner | Nonprofit1 |  |  |  |  | Higher education | 1142000 |  |  |  | Current expenses - depreciation |  | Estonia |  |  |  |  | General | TG_general | Museums (and other visual arts institutions) | x | [9 empty] | Number of awareness raising campaigns carried out | Output | Binding | ACC_OTC1_OTP3_IND2 | Number | Project Promoters’ records, Audio/video/print material | Semi-annually | 0 | N/A | 18 | [7 empty] | Likely_Serious | 3 | [10 empty] | 2.2 Electrical engineering, electronic engineering, information engineering
|  | Zvolen |  |  |  | Religious institutions | Foundation | 90% |  |  |  | Health |  |  |  |  | Current expenses - other |  | Finland | [6 empty] | Performing arts institutions | x | [9 empty] | Number of new outdoor climate change mitigation and adaptation measures completed | Output | Binding | ACC_OTC1_OTP4_IND1 | Number | Project Promoters´ records | Semi-annually | 0 | N/A | 7 | [7 empty] | Likely_Very serious | 3.46 | [10 empty] | 2.3 Mechanical engineering
|  | Žarnovica |  |  |  | Private | Civic association (o.z.) | 90% |  |  |  | Health policy and administrative management | 1211000 | [5 empty] | France | [6 empty] | TG_education | [10 empty] | Estimated annual reduced energy/electricity consumption (in kWh) | Output | Binding | ACC_OTC1_OTP4_IND2 | Annual number | Project Promoters´ records | Semi-annually | 0 | N/A | TBC | [7 empty] | Almost certain_Minimal | 2 | [10 empty] | 2.4 Chemical engineering
|  | Žiar nad Hronom |  |  |  | Large enterprise | Non-investment fund (n.f.) | 90% |  |  |  | Food safety | 1211001 | [5 empty] | Ireland | [6 empty] | Students (any age) |  | x | [8 empty] | Number of students completing educational activities/courses | Output | Binding | ACC_OTC1_OTP4_IND3 | Number | Project Promoter’s records, Attendance sheets | Semi-annually | 0 | N/A | 1200 | [7 empty] | Almost certain_Moderate | 2.83 | [10 empty] | 2.5 Materials engineering
|  | Bratislavský |  |  |  | Small and medium sized enterprise | Non-profit organisation providing services in general interest (n.o.) | 90% |  |  |  | Medical education/training | 1218100 | [5 empty] | Italy | [6 empty] | NEETs (not in education, employment or training) |  | x | [8 empty] | Number of local decisionmakers and administrators completing workshops/courses | Output | Binding | ACC_OTC1_OTP4_IND4 | Number | Project Promoter’s records, Attendance sheets | Semi-annually | 0 | N/A | 360 | [7 empty] | Almost certain_Serious | 3.46 | [10 empty] | 2.6 Medical engineering
|  | Malacky |  |  |  | Micro enterprise | Churches and religious institutions | 90% |  |  |  | Health data systems | 1218201 | [5 empty] | Cyprus | [6 empty] | Teachers/Professors (any level) | x | [9 empty] | indicators_ACC_OTC2 |  |  | __ | [13 empty] | Almost certain_Very serious | 4 | [10 empty] | 2.7 Environmental engineering
|  | Bratislava I |  |  |  | Public-Private organisation | Community association | 90% |  |  |  | Medical services | 1219100 | [5 empty] | Lithuania | [6 empty] | Educational institution staff (non-teaching) | x | [9 empty] | Estimated number of people benefiting from ecosystems improvement measures | Outcome | Reported | ACC_OTC2_IND1 | Number | Statistical data (Statistical Office of the Slovak Republic), Survey results | 2022, 2025 | 0 | N/A | 3000 | [19 empty] | 2.8 Environmental biotechnology
|  | Bratislava II |  |  |  |  | Social enterprises | 90% |  |  |  | Mental health services | 1219101 | [5 empty] | Latvia | [6 empty] | Researchers/Scientists |  | x | [8 empty] | Improved environmental status of supported ecosystems | Outcome | Reported | ACC_OTC2_IND2 | Binary | Survey results | 2022, 2025 | No | 2017 | Yes | [19 empty] | 2.9 Industrial Biotechnology
|  | Bratislava III |  |  |  |  | Trade union or association | 90% |  |  |  | Cancer services | 1219102 | [5 empty] | Luxembourg | [6 empty] | Universities/Research institutions | x | [9 empty] | Estimated area of wetland ecosystems restored (in m2) | Output | Binding | ACC_OTC2_OTP1_IND1 | Number | Project Promoters´ records | Semi-annually | 0 | N/A | 600 | [19 empty] | 2.10 Nano-technology
|  | Bratislava IV |  |  |  |  | Employers' organisation | 90% |  |  |  | Basic health care | 1222000 | [5 empty] | Hungary | [6 empty] | TG_health | [10 empty] | Number of awareness campaigns carried out | Output | Binding | ACC_OTC2_OTP1_IND2 | Number | Project Promoters’ records, Audio/video/print material | Semi-annually | 0 | N/A | 6 | [19 empty] | 2.11 Other engineering and technologies
|  | Bratislava V |  |  |  |  | Professional associations | 90% |  |  |  | Basic health infrastructure | 1223000 | [5 empty] | Malta | [6 empty] | Medical staff | x | [9 empty] | Number of wetland ecosystems supported | Output | Binding | ACC_OTC2_OTP1_IND3 | Number | Project Promoters´ records, Audio/video/print | Semi-annually | 0 | N/A | 6 | [19 empty] | medical_fields
|  | Senec |  |  |  |  | Other civil society groups and institution | 90% |  |  |  | Infectious disease control | 1225000 | [5 empty] | Germany | [6 empty] | People with disabilities (excluding people with mental health problems) |  | x | [8 empty] | indicators_ACC_OTCB |  |  | __ | [25 empty] | 3.1 Basic medicine
|  | Pezinok |  |  |  |  | Private1 |  |  |  |  | Health education | 1226100 | [5 empty] | Netherland | [6 empty] | People with mental health problems |  | x | [8 empty] | Level of satisfaction with the partnership (disaggregated by State type) | Outcome | Reported | ACC_OTCB_IND1 | Scale 1-7 | Survey results | Annually (APR) | TBD | N/A | ≥4.5 and an increase on the baseline | [19 empty] | 3.2 Clinical medicine
|  | Košický |  |  |  |  | Joint stock company (a.s.) | 90% |  |  |  | Health promotion | 1226101 | [5 empty] | Poland | [6 empty] | People with communicable diseases (incl. TB and HIV/AIDS) |  | x | [8 empty] | Level of trust between cooperating entities in Beneficiary States and Donor States (disaggregated by State type) | Outcome | Reported | ACC_OTCB_IND2 | Scale 1-7 | Survey results | Annually (APR) | TBD | N/A | ≥4.5 and an increase on the baseline | [19 empty] | 3.3 Health sciences
|  | Michalovce |  |  |  |  | Limited company (s.r.o.) | 90% |  |  |  | Tuberculosis control | 1226300 | [5 empty] | Portugal | [6 empty] | People with addictions (alcohol, drugs, etc.) |  | x | [8 empty] | Share of cooperating organisations that apply the knowledge acquired from bilateral partnership (disaggregated by State type) | Outcome | Reported | ACC_OTCB_IND3 | Percentage | Survey results | Annually (APR) | N/A | N/A | 60 | [19 empty] | 3.4 Health biotechnology
|  | Košice I |  |  |  |  | Limited partnership (k.s.) | 90% |  |  |  | Health personnel development | 1228100 | [5 empty] | Austria | [6 empty] | TG_justice | [10 empty] | Number of Projects involving cooperation with a Donor Project Partner (disaggregated by Donor State) | Output | Binding | ACC_OTCB_OTP1_IND1 | Number | Copies of contracts concluded with Project Promoters, Partnership agreements between Project Promoters and project partners | Semi-annually | 0 | N/A | 36 | [19 empty] | 3.5 Other medical sciences
|  | Košice II |  |  |  |  | Public limited company (v.o.s.) | 90% |  |  |  | Reproductive health care | 1302000 | [5 empty] | Romania | [6 empty] | Judges | x | [9 empty] | Number of training courses co-organised by donor state and beneficiary state entities | Output | Binding | ACC_OTCB_OTP1_IND2 | Number | Project Promoter's records | Semi-annually | 0 | N/A | 10 | [19 empty] | agriculture_fields
|  | Košice III |  |  |  |  | Cooperative corporation (družstvo) | 90% |  |  |  | STD control including HIV/AIDS | 1304000 | [5 empty] | Greece | [6 empty] | Police | x | [38 empty] | 4.1 Agriculture, forestry, and fisheries
|  | Košice IV |  |  |  |  | Association of legal entities (z.z.p.o.) | 90% |  |  |  | Government | [6 empty] | Slovenia | [6 empty] | Border guards | x | [38 empty] | 4.2 Animal and dairy science
|  | Košice-okolie |  |  |  |  | Other - specify | 90% |  |  |  | Public sector policy and administrative management | 1511000 | [5 empty] | United Kingdom | [6 empty] | Prison/Probation authorities/staff | x | [38 empty] | 4.3 Veterinary science
|  | Gelnica | [9 empty] | Gender policy, management and administration | 1511002 | [5 empty] | Spain | [6 empty] | Prosecutors | x | [38 empty] | 4.4 Agricultural biotechnology
|  | Rožňava | [9 empty] | Decentralisation and support to subnational government | 1511200 | [5 empty] | Sweden | [6 empty] | Juvenile criminal offenders |  | x | [37 empty] | 4.5 Other agricultural sciences
|  | Trebišov | [9 empty] | Anti-corruption organisations and institutions | 1511300 | [5 empty] | Other | [6 empty] | Criminal offenders (incl. prisoners and offenders following alternative sanctions) |  | x | [37 empty] | social_fields
|  | Spišská Nová Ves | [9 empty] | Legal and judicial development | 1513000 | [12 empty] | Victims of hate crime/hate speech |  | x | [37 empty] | 5.1 Psychology
|  | Sobrance | [9 empty] | Transparency | 1513001 | [12 empty] | Victims of domestic violence/gender-based violence |  | x | [37 empty] | 5.2 Economics and business
|  | Nitriansky | [9 empty] | Probation services | 1513003 | [12 empty] | Victims of human trafficking |  | x | [37 empty] | 5.3 Educational sciences
|  | Levice | [9 empty] | Alternative dispute resolution | 1513004 | [12 empty] | TG_migration | [39 empty] | 5.3 Sociology
|  | Komárno | [9 empty] | Legal aid, counsel, treatment and shelters | 1513005 | [12 empty] | Asylum authorities/staff | x | [38 empty] | 5.5 Law
|  | Nové Zámky | [9 empty] | Border management | 1513006 | [12 empty] | Unaccompanied asylum-seeking children |  | x | [37 empty] | 5.6 Political Science
|  | Nitra | [9 empty] | Countering organized crime | 1513007 | [12 empty] | Asylum-seekers |  | x | [37 empty] | 5.7 Social and economic geography
|  | Topoľčany | [9 empty] | Countering trafficking | 1513008 | [12 empty] | TG_minority | [39 empty] | 5.8 Media and communications
|  | Šaľa | [9 empty] | Crime prevention | 1513009 | [12 empty] | Jewish population |  | x | [37 empty] | 5.9 Other social sciences
|  | Zlaté Moravce | [9 empty] | Police | 1513200 | [12 empty] | Lesbian, gay, bisexual, transgender, intersex population (LGBTI) |  | x | [37 empty] | humanities_fields
|  | Prešovský | [9 empty] | Ombudsman | 1513500 | [12 empty] | Muslim population |  | x | [37 empty] | 6.1 History and archaeology
|  | Medzilaborce | [9 empty] | Immigration | 1513600 | [12 empty] | Roma population |  | x | [37 empty] | 6.2 Languages and literature
|  | Levoča | [9 empty] | Prisons | 1513700 | [12 empty] | Roma mediators | x | [38 empty] | 6.3 Philosophy, ethics and religion
|  | Kežmarok | [9 empty] | Democratic participation and civil society | 1515000 | [12 empty] | Russian-speaking minorities |  | x | [37 empty] | 6.4 Art (arts, history of arts, performing arts, music)
|  | Bardejov | [9 empty] | Elections | 1515100 | [12 empty] | Other minorities |  | x | [37 empty] | 6.5 Other humanities
|  | Humenné | [9 empty] | Media and free flow of information | 1515300 | [12 empty] | TG_policy
|  | Sabinov | [9 empty] | Human rights | 1516000 | [12 empty] | Politicians (at national or sub-national level) | x
|  | Poprad | [9 empty] | Hate speech/hate crime | 1516004 | [12 empty] | Public institutions (at national or sub-national level) | x
|  | Prešov | [9 empty] | Domestic and gender based violence | 1516005 | [12 empty] | Civil society organisations | x | x
|  | Svidník | [9 empty] | Multicultural awareness | 1516020 | [12 empty] | TG_work
|  | Snina | [9 empty] | Gender equality organisations and institutions | 1517000 | [12 empty] | Trade unions | x
|  | Stará Ľubovňa | [9 empty] | Local government administration | 1518500 | [12 empty] | Employers' organisations | x
|  | Stropkov | [9 empty] | Urban development and management | 1518501 | [12 empty] | Labour inspectorates | x
|  | Vranov nad Topľou | [9 empty] | Statistical capacity building | 1606200 | [12 empty] | Unemployed |  | x
|  | Trenčiansky | [9 empty] | Social_Infrastructure | [13 empty] | Employees/workers |  | x
|  | Myjava | [9 empty] | Jewish cultural history | 1516010 | [12 empty] | TG_general
|  | Ilava | [9 empty] | Social/ welfare services | 1601000 | [12 empty] | Media | x
|  | Bánovce nad Bebravou | [9 empty] | Employment policy and administrative management | 1602000 | [12 empty] | People at risk of poverty/in poverty16 |  | x
|  | Púchov | [9 empty] | Gender equality in employment | 1602001 | [12 empty] | Women |  | x
|  | Prievidza | [9 empty] | Housing policy and administrative management | 1603000 | [12 empty] | Men |  | x
|  | Partizánske | [9 empty] | Low-cost housing | 1604000 | [12 empty] | General public |  | x
|  | Nové Mesto nad Váhom | [9 empty] | Multisector aid for basic social services | 1605000 | [12 empty] | Environment |  | x
|  | Považská Bystrica | [9 empty] | Culture and recreation | 1606100
|  | Trenčín | [9 empty] | Cultural heritage management, preservation and conservation | 1606116
|  | Trnavský | [9 empty] | Creative and artistic cultural activities | 1606117
|  | Galanta | [9 empty] | Social and economic development through culture | 1606118
|  | Dunajská Streda | [9 empty] | Social mitigation of HIV/AIDS | 1606400
|  | Hlohovec | [9 empty] | Energy
|  | Skalica | [9 empty] | Energy Efficiency | 2303001
|  | Senica | [9 empty] | Energy security | 2303002
|  | Piešťany | [9 empty] | Energy policy and administrative management | 2311000
|  | Trnava | [9 empty] | Energy education/training | 2318100
|  | Žilinský | [9 empty] | Energy generation, renewable sources – multiple technologies | 2321000
|  | Námestovo | [9 empty] | Hydro-electric power plants | 2322000
|  | Martin | [9 empty] | Solar energy | 2323000
|  | Liptovský Mikuláš | [9 empty] | Wind energy | 2324000
|  | Kysucké Nové Mesto | [9 empty] | Marine energy | 2325000
|  | Dolný Kubín | [9 empty] | Geothermal energy | 2326000
|  | Čadca | [9 empty] | Bio energy | 2327000
|  | Bytča | [9 empty] | Hybrid energy | 2341000
|  | Ružomberok | [9 empty] | Business
|  | Tvrdošín | [9 empty] | Business support services and institutions | 2501000
|  | Turčianske Teplice | [9 empty] | Technological innovation and development | 3218200
|  | Žilina | [9 empty] | Blue growth | 3218201
[12 empty] | Green growth | 3218202
[12 empty] | Welfare and heath technologies | 3218203
Environment
[12 empty] | Environmental policy and administrative management | 4101000
[12 empty] | Marine and inland water management | 4101001
[12 empty] | Spatial planning | 4101002
[12 empty] | Climate Change policy and administrative management | 4101003
[12 empty] | Climate change mitigation | 4101004
[12 empty] | Carbon capture and storage | 4101005
[12 empty] | Climate change adaptation | 4101006
[12 empty] | Air pollution control | 4102001
[12 empty] | Greenhouse gas reduction | 4102004
[12 empty] | Hazardous substance | 4102005
[12 empty] | Waste / Recycling | 4102006
[12 empty] | Circular economy | 4102007
[12 empty] | Bio-diversity | 4103000
[12 empty] | Red list species | 4103001
[12 empty] | Flood prevention/control | 4105000
[12 empty] | Drought prevention | 4105801
[12 empty] | Environment and Climate Change education/training | 4108100
Multisector
[12 empty] | Educational research | 1118200
[12 empty] | Medical research | 1218200
[12 empty] | Energy research | 2318200
[12 empty] | Agricultural research | 3118200
[12 empty] | Forestry research | 3128200
[12 empty] | Fishery research | 3138200
[12 empty] | Environmental research | 4108200
[12 empty] | Research/scientific institutions | 4308200
[12 empty] | Climate change research | 4308201
[12 empty] | Carbon capture and storage research | 4308202
[12 empty] | Marine research | 4308203
[12 empty] | Gender research | 4308204
[12 empty] | Health research | 4308205
[12 empty] | Energy research | 4308206
[12 empty] | Social science and humanities research | 4308208
[12 empty] | Fire and rescue services | 1513300
Migration
[12 empty] | Migration policy and administrative management system | 9301001

## Errors (hidden)
Formula | Result | Error_EN | Error_SK
ISERROR(VLOOKUP(sector_specified;grant_rates_table;2;FALSE)) | FALSE | Data not available. Please fill in point 2.1.3 | Údaje nie sú k dispozícii. Vyplňte prosím bod 2.1.3.
IF(project_grant_rate>maximum_grant_rate) | FALSE | If using cash co-financing only, you need to increase your co-financing to EUR 88714 | Ak použávate len peňažné spolufinancovanie, musíte zvýšiť vaše spolufinancovanie na 43714 eur.
IF(AND(sector=nonprofit_sector_verification_title;sector_specified<>churches_verification_title;project_grant_rate>maximum_grant_rate);TRUE) | FALSE | If using in-kind, in-kind cofinancing should be equal to the figure in point 5.1.17, i.e. EUR 44376 | Ak využívate príspevky v naturáliách, spolufinancovanie v naturáliách by sa malo rovnať údaju v časti 5.1.17, t.j. 44376 eur.
IF(AND(sector=nonprofit_sector_verification_title;sector_specified<>churches_verification_title;maximum_in_kind_percentage=0,5;project_grant_rate>maximum_grant_rate);TRUE) | FALSE | In this case, cash-cofinancing should be equal to the the same figure, i.e. EUR 44376 | V tomto prípade by sa peňažné spolufinancovanie malo tiež rovnať tejto hodnote, t.j. 44376 eur.
grant_requested_total>maximum_project_grant_requested | FALSE | Project grant is too high. You shall decrease your costs | Projektový grant je príliš vysoký. Musíte znížiť náklady.
grant_requested_total<maximum_project_grant_requested | FALSE | Project grant is too low. You shall increase your costs | Projektový grant je príliš nízky. Musíte zvýšiť náklady.
actual_in_kind_percentage>maximum_in_kind_percentage | FALSE | You have to decrease in_kind contributions or increase cash-cofinancing. | Musíte znížiť príspevky v naturáliách alebo tvýšiť peňažné spolufinancovanie.
reserve_total>maximum_reserve | FALSE | You have to decrease the reserve | Musíte znížiť rezervu.